## Dashboard
BUDGET & COST TRACKER — Government Contract Remote Surge Hiring
Prepared for Kelly ¦ Generated: 20 April 2026 ¦ Plain Dealing, LA
EXECUTIVE SUMMARY
Total Budget | Total Spent | Remaining Budget | Burn Rate ($/day) | Projected Final Cost | Variance ($)
Variance (%) |  | Overall Status |  | Cost Per Hire
COST BREAKDOWN BY CATEGORY
Category | Budgeted | Actual | Variance ($) | Variance (%) | Status
Recruiting
Equipment/IT
Training
Personnel
Background/Clearance
Overhead
Contingency
BUDGET vs ACTUAL BY PHASE
Phase | Budgeted | Actual | Variance ($) | Variance (%) | Status
Pre-Planning | 25000 | 18500
Activation | 85000 | 78300
Onboarding | 150000 | 142900
Sustain | 180000 | 0
Close-Out | 30000 | 0
MONTHLY BURN RATE TREND | [5 empty] | TRAFFIC LIGHT LEGEND
Month | Planned Spend | Actual Spend | Cumulative Actual |  |  | ● | Green — Under Budget (>10% remaining)
Month 1 | [5 empty] | ● | Yellow — On Track (within 10%)
Month 2 | [5 empty] | ● | Red — Over Budget (exceeds budget)
Month 3
Month 4
Month 5
Month 6
Month 7
Month 8
Month 9
Month 10
Month 11
Month 12

## Budget Plan
Budget Plan — Government Contract Remote Surge Hiring
Line Item | Category | Description | Unit Cost | Quantity | Total Budgeted | Approved By | Approval Date | Notes
Job Board Postings (USAJobs, ClearanceJobs) | Recruiting | Annual posting fees for multiple job boards | 2500 | 6
Recruiter Hours — Internal | Recruiting | Dedicated recruiter FTE hours for surge | 75 | 480
Assessment Tools & Licensing | Recruiting | Pre-hire cognitive and skills assessment platform | 15 | 200
Travel for Interviews | Recruiting | Candidate travel reimbursement for in-person interviews | 800 | 10
Referral Bonuses | Recruiting | Employee referral bonus per successful hire | 1500 | 20
Staffing Agency Fees | Recruiting | Third-party staffing agency placement fees | 5000 | 10
Laptops (Gov-Spec) | Equipment/IT | FIPS 140-2 compliant laptops with encryption | 1800 | 50
External Monitors | Equipment/IT | 24-inch IPS monitors for remote workstations | 350 | 50
Headsets (VOIP-Compatible) | Equipment/IT | Noise-cancelling USB headsets | 120 | 50
CAC Readers | Equipment/IT | USB smart card readers for PIV/CAC authentication | 45 | 55
Keyboards & Mice Kits | Equipment/IT | Ergonomic keyboard and mouse combo | 80 | 50
Webcams (HD Secure) | Equipment/IT | 1080p webcams with privacy shutters | 95 | 50
Shipping & Logistics | Equipment/IT | Overnight shipping of equipment kits to new hires | 65 | 55
Surge Pricing Premiums | Equipment/IT | Premium markup for expedited procurement | 200 | 50
LMS Licenses | Training | Learning management system per-seat licenses | 50 | 60
Training Materials & Curriculum | Training | Custom course development and printed materials | 5000 | 3
Instructor / Facilitator Costs | Training | Contract instructor daily rate for live training | 1200 | 20
Simulation & Lab Tools | Training | Virtual lab environment licenses for hands-on training | 300 | 50
Certification Exam Fees | Training | Industry certification exam vouchers | 400 | 30
Salary Costs — Ramp Period | Personnel | New hire salary during 30-day ramp/training | 4500 | 50
Overtime — Existing Staff | Personnel | OT for current staff supporting surge operations | 60 | 800
Temporary Staffing Augmentation | Personnel | Temp staff to backfill during surge | 3500 | 5
Contractor Premiums | Personnel | Premium rates for 1099 contractors vs FTEs | 2000 | 10
e-QIP Processing Fees | Background/Clearance | Electronic questionnaire processing per applicant | 350 | 60
Interim Clearance Processing | Background/Clearance | Expedited interim secret clearance costs | 500 | 50
Drug Testing | Background/Clearance | Pre-employment 10-panel drug screening | 85 | 60
Fingerprinting (Live Scan) | Background/Clearance | FBI/State fingerprint capture and submission | 50 | 60
Polygraph Examinations | Background/Clearance | Full-scope polygraph for TS/SCI positions | 2500 | 15
VPN & Remote Access Licenses | Overhead | Per-user VPN client licenses (annual) | 120 | 55
Collaboration Tools (MS Teams/Zoom) | Overhead | Enterprise collaboration platform licenses | 30 | 55
IT Help Desk Support Augmentation | Overhead | Additional help desk FTEs for onboarding surge | 4500 | 3
Facilities / Hoteling Space | Overhead | Shared desk/hoteling reservations for hybrid workers | 500 | 20
Contingency Reserve (10%) | Contingency | 10% contingency on total budgeted amount | 1 | 1
CATEGORY SUMMARY
Category | Total Budgeted
Recruiting
Equipment/IT
Training
Personnel
Background/Clearance
Overhead
Contingency
GRAND TOTAL

## Expenditure Log
Expenditure Log — Surge Hiring Operations
Date | Vendor/Payee | Description | Category | Line Item Reference | Invoice Number | Amount | Payment Method | Payment Status | Approved By | GL Code | Contract CLIN | Running Total | Notes
2026-01-05 | ClearanceJobs.com | Q1 Job Board Posting Package | Recruiting | Job Board Postings | INV-10001 | 2500 | Invoice | Paid | J. Martinez | 6100-01 | CLIN 0001
2026-01-08 | Dell Technologies | Lot 1 — 20x Latitude 5540 Laptops | Equipment/IT | Laptops (Gov-Spec) | INV-10002 | 36000 | Invoice | Paid | J. Martinez | 6200-01 | CLIN 0002
2026-01-10 | Amazon Business | 20x USB Headsets — Jabra Evolve2 | Equipment/IT | Headsets (VOIP-Compatible) | INV-10003 | 2400 | P-Card | Paid | S. Nguyen | 6200-02 | CLIN 0002
2026-01-12 | HireVue Inc. | Assessment Platform — 100 seat license | Recruiting | Assessment Tools & Licensing | INV-10004 | 3000 | Invoice | Paid | J. Martinez | 6100-02 | CLIN 0001
2026-01-15 | CACI International | Staffing Agency — 3 placements | Recruiting | Staffing Agency Fees | INV-10005 | 15000 | Invoice | Paid | R. Thompson | 6100-03 | CLIN 0001
2026-01-20 | Cornerstone OnDemand | LMS Licenses — 60 seats | Training | LMS Licenses | INV-10006 | 3000 | Invoice | Approved | S. Nguyen | 6300-01 | CLIN 0003
2026-02-01 | Internal Payroll | Recruiter OT — Jan cycle | Personnel | Overtime — Existing Staff | PAY-20001 | 4800 | ACH | Paid | R. Thompson | 6400-01 | CLIN 0004
2026-02-05 | DCSA/OPM | e-QIP Processing — Batch 1 (20 applicants) | Background/Clearance | e-QIP Processing Fees | GOV-30001 | 7000 | Check | Paid | J. Martinez | 6500-01 | CLIN 0005
2026-02-10 | Quest Diagnostics | Drug Screening — 25 candidates | Background/Clearance | Drug Testing | INV-10007 | 2125 | P-Card | Paid | S. Nguyen | 6500-02 | CLIN 0005
2026-02-15 | FedEx | Equipment Shipping — Batch 1 | Equipment/IT | Shipping & Logistics | INV-10008 | 1300 | P-Card | Paid | S. Nguyen | 6200-03 | CLIN 0002
2026-02-20 | Cisco Systems | VPN Licenses — 55 users | Overhead | VPN & Remote Access Licenses | INV-10009 | 6600 | Invoice | Approved | R. Thompson | 6600-01 | CLIN 0006
2026-03-01 | Booz Allen Hamilton | Contract Instructor — Week 1 | Training | Instructor / Facilitator Costs | INV-10010 | 6000 | Invoice | Paid | J. Martinez | 6300-02 | CLIN 0003
2026-03-05 | Internal Payroll | New Hire Salaries — Ramp Cohort 1 (15) | Personnel | Salary Costs — Ramp Period | PAY-20002 | 67500 | ACH | Paid | R. Thompson | 6400-02 | CLIN 0004
2026-03-10 | IdentoGO | Fingerprinting — 30 applicants | Background/Clearance | Fingerprinting (Live Scan) | INV-10011 | 1500 | P-Card | Pending | S. Nguyen | 6500-03 | CLIN 0005
2026-03-15 | Microsoft | Teams E5 Licenses — 55 seats | Overhead | Collaboration Tools (MS Teams/Zoom) | INV-10012 | 1650 | Invoice | Paid | R. Thompson | 6600-02 | CLIN 0006
2026-03-20 | CompTIA | Security+ Exam Vouchers — 15 | Training | Certification Exam Fees | INV-10013 | 6000 | Invoice | Disputed | J. Martinez | 6300-03 | CLIN 0003
2026-04-01 | Dell Technologies | Lot 2 — 15x Monitors + Peripherals | Equipment/IT | External Monitors | INV-10014 | 5250 | Invoice | Pending | S. Nguyen | 6200-04 | CLIN 0002
2026-04-05 | Internal Payroll | New Hire Salaries — Ramp Cohort 2 (10) | Personnel | Salary Costs — Ramp Period | PAY-20003 | 45000 | ACH | Approved | R. Thompson | 6400-02 | CLIN 0004
2026-04-10 | Polygraph Associates LLC | Full-Scope Poly — 5 candidates | Background/Clearance | Polygraph Examinations | INV-10015 | 12500 | Invoice | Pending | J. Martinez | 6500-04 | CLIN 0005
2026-04-15 | WeWork | Hoteling — 10 desks x 2 months | Overhead | Facilities / Hoteling Space | INV-10016 | 10000 | Invoice | Approved | R. Thompson | 6600-03 | CLIN 0006

## Cost Per Hire Analysis
Cost Per Hire Analysis — Surge Hiring Operation
Employee Name | Position | Clearance Level | Start Date | Recruiting Cost | Background/Clearance Cost | Equipment Cost | Training Cost | Onboarding Cost | Total Cost to Hire | Days to Fill | Cost Per Day
Adams, Sarah | IT Specialist | Secret | 2026-02-10 | 3200 | 1450 | 2540 | 1800 | 500 |  | 45
Brooks, James | Cybersecurity Analyst | TS/SCI | 2026-02-15 | 4500 | 3850 | 2540 | 2200 | 600 |  | 62
Chen, Wei | Help Desk Technician | Public Trust | 2026-02-18 | 1800 | 485 | 2340 | 1200 | 400 |  | 28
Davis, Marcus | Systems Administrator | Secret | 2026-02-24 | 3500 | 1450 | 2540 | 1800 | 500 |  | 38
Evans, Patricia | Network Engineer | TS/SCI | 2026-03-02 | 5200 | 3850 | 2740 | 2200 | 650 |  | 70
Foster, Andre | Program Analyst | Secret | 2026-03-05 | 2800 | 1450 | 2340 | 1500 | 450 |  | 35
Garcia, Maria | Data Analyst | Secret | 2026-03-10 | 2600 | 1450 | 2540 | 1600 | 500 |  | 33
Harris, Tyrone | SOC Analyst | TS/SCI | 2026-03-15 | 4800 | 3850 | 2740 | 2400 | 700 |  | 58
Irving, Lisa | Technical Writer | Public Trust | 2026-03-18 | 1500 | 485 | 2140 | 1000 | 350 |  | 22
Johnson, Robert | Cloud Engineer | Secret | 2026-03-25 | 4200 | 1450 | 2740 | 2000 | 550 |  | 48
Kim, Daniel | Information Assurance | TS/SCI | 2026-04-01 | 5500 | 3850 | 2540 | 2400 | 750 |  | 75
Lopez, Carmen | Help Desk Technician | Public Trust | 2026-04-05 | 1600 | 485 | 2340 | 1200 | 400 |  | 25
Mitchell, David | Database Administrator | Secret | 2026-04-08 | 3800 | 1450 | 2540 | 1800 | 550 |  | 42
Nguyen, Thanh | Software Developer | TS/SCI | 2026-04-12 | 5800 | 3850 | 2740 | 2600 | 800 |  | 68
O'Brien, Kathleen | Project Coordinator | Secret | 2026-04-15 | 2400 | 1450 | 2340 | 1400 | 450 |  | 30
SUMMARY STATISTICS |  |  | BREAKDOWN BY POSITION TYPE
Metric | Value |  | Position | Count | Avg Cost | Avg Days
Average Cost Per Hire |  |  | Cloud Engineer
Median Cost Per Hire |  |  | Cybersecurity Analyst
Highest Cost Hire |  |  | Data Analyst
Lowest Cost Hire |  |  | Database Administrator
Average Days to Fill |  |  | Help Desk Technician
Total Hires |  |  | IT Specialist
Total Recruiting Spend |  |  | Information Assurance
Network Engineer
Program Analyst
Project Coordinator
SOC Analyst
Software Developer
Systems Administrator
Technical Writer
BREAKDOWN BY CLEARANCE LEVEL
|  |  | Clearance Level | Count | Avg Cost | Avg Days
Public Trust
Secret
TS/SCI

## Variance Report
Variance Report — Budget vs Actual
Category | Budgeted Amount | Actual Amount | Variance ($) | Variance (%) | Status | Explanation | Corrective Action
Recruiting
Equipment/IT
Training
Personnel
Background/Clearance
Overhead
Contingency
TOTAL

## Forecast
12-Month Forecast — Surge Hiring Budget
|  | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Annual Total
PLANNED SPEND
| Recruiting | 12000 | 15000 | 10000 | 8000 | 5000 | 3000 | 2000 | 1000 | 1000 | 500 | 500 | 500
| Equipment/IT | 20000 | 25000 | 15000 | 10000 | 5000 | 3000 | 2000 | 1000 | 1000 | 500 | 500 | 500
| Training | 2000 | 5000 | 10000 | 8000 | 6000 | 4000 | 3000 | 2000 | 1500 | 1000 | 500 | 500
| Personnel | 5000 | 20000 | 45000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
| Background/Clearance | 5000 | 8000 | 6000 | 4000 | 2000 | 1000 | 500 | 500 | 500 | 500 | 500 | 500
| Overhead | 3000 | 5000 | 6000 | 6000 | 5000 | 5000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000
| Contingency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Planned
ACTUAL SPEND
| Recruiting | 13500 | 18500 | 8000 | 6400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Equipment/IT | 22000 | 23700 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Training | 1500 | 3000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Personnel | 4800 | 0 | 67500 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Background/Clearance | 0 | 9125 | 1500 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overhead | 0 | 6600 | 1650 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Contingency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Actual
CUMULATIVE COMPARISON
Cumulative Planned
Cumulative Actual
Cumulative Variance
PROJECTIONS | bar: Month 1
Metric | Value
Total Budget (Planned)
Actual Spend to Date
Remaining Planned
Estimate at Completion (EAC)
Estimate to Complete (ETC)
Variance at Completion (VAC)
Cost Performance Index (CPI)