## Dashboard
Equipment & IT Asset Tracker — Government Contract Remote Surge Hiring
Dashboard Overview — Updated 04/20/2026 6:49 PM CDT
ASSET SUMMARY | BREAKDOWN BY EQUIPMENT TYPE
Total Assets | Equipment Type | Count | Deployed | Value
Assets Deployed | Laptop
Assets In Transit | Monitor
Assets In Stock | Headset
Assets Configured | CAC Reader
Assets Pending Return | Keyboard/Mouse
Assets Returned | Webcam
Total Asset Value | Docking Station
Monthly Shipping Cost (Est.) | Mobile Phone
Printer
Software License
FULFILLMENT & READINESS | Other
Equipment Fulfillment Rate | Total
Fulfillment Status
Workspace Approval Rate | STATUS DISTRIBUTION |  |  |  | OPEN ALERTS SUMMARY
Workspace Status | Status | Count |  |  | Priority | Open | In Progress
| In Stock |  |  |  | High
| Configured |  |  |  | Medium
SHIPPING & RETURNS PERFORMANCE | Shipped |  |  |  | Low
Avg Days: Order to Delivery | Deployed |  |  |  | Total
Overdue Returns Count | Return Requested
Overdue Return Liability | Returned
Returns Compliance | Lost
Damaged
Disposed

## Asset Inventory
Asset ID | Asset Tag | Equipment Type | Make/Model | Serial Number | Purchase Date | Purchase Cost | Vendor | PO Number | Warranty Expiration | Condition | Current Status | Assigned To | Assignment Date | Location | Notes
AST-001 | LPT-001 | Laptop | Dell Latitude 5540 | DL5540-A1B2C3 | 2026-01-10 | 1249.99 | Dell Technologies | PO-2026-001 | 2029-01-10 | New | Deployed | Maria Santos | 2026-02-15 | Employee Home
AST-002 | LPT-002 | Laptop | Dell Latitude 5540 | DL5540-D4E5F6 | 2026-01-10 | 1249.99 | Dell Technologies | PO-2026-001 | 2029-01-10 | New | Deployed | James Carter | 2026-02-16 | Employee Home
AST-003 | LPT-003 | Laptop | Dell Latitude 5540 | DL5540-G7H8I9 | 2026-01-10 | 1249.99 | Dell Technologies | PO-2026-001 | 2029-01-10 | New | Shipped |  |  | In Transit | Shipping to new hire
AST-004 | LPT-004 | Laptop | HP EliteBook 840 G9 | HPE840-J1K2L3 | 2025-11-05 | 1189 | HP Inc. | PO-2025-042 | 2028-11-05 | Good | Deployed | Aisha Johnson | 2026-01-20 | Employee Home
AST-005 | LPT-005 | Laptop | HP EliteBook 840 G9 | HPE840-M4N5O6 | 2025-11-05 | 1189 | HP Inc. | PO-2025-042 | 2028-11-05 | Good | Return Requested | David Kim | 2026-01-22 | Employee Home | Separation 4/30
AST-006 | MON-001 | Monitor | Dell U2723QE 27" | DLM27-P7Q8R9 | 2026-01-15 | 489.99 | Dell Technologies | PO-2026-002 | 2029-01-15 | New | Deployed | Maria Santos | 2026-02-15 | Employee Home
AST-007 | MON-002 | Monitor | Dell U2723QE 27" | DLM27-S1T2U3 | 2026-01-15 | 489.99 | Dell Technologies | PO-2026-002 | 2029-01-15 | New | Deployed | James Carter | 2026-02-16 | Employee Home
AST-008 | MON-003 | Monitor | LG 27UK850-W | LG27-V4W5X6 | 2025-08-20 | 449 | CDW | PO-2025-030 | 2026-08-20 | Good | In Stock |  |  | Warehouse
AST-009 | MON-004 | Monitor | LG 27UK850-W | LG27-Y7Z8A1 | 2025-08-20 | 449 | CDW | PO-2025-030 | 2026-05-20 | Fair | Returned | Tom Reed | 2025-10-01 | Warehouse | Minor scratch on bezel
AST-010 | HDS-001 | Headset | Jabra Evolve2 75 | JBR75-B2C3D4 | 2026-02-01 | 229.99 | Jabra Direct | PO-2026-005 | 2028-02-01 | New | Deployed | Maria Santos | 2026-02-15 | Employee Home
AST-011 | HDS-002 | Headset | Jabra Evolve2 75 | JBR75-E5F6G7 | 2026-02-01 | 229.99 | Jabra Direct | PO-2026-005 | 2028-02-01 | New | Deployed | Aisha Johnson | 2026-02-18 | Employee Home
AST-012 | HDS-003 | Headset | Poly Voyager Focus 2 | PLY-H8I9J1 | 2025-09-10 | 199.99 | CDW | PO-2025-035 | 2027-09-10 | Good | In Stock |  |  | Warehouse
AST-013 | CAC-001 | CAC Reader | HID Omnikey 3121 | HID-K2L3M4 | 2026-01-20 | 34.99 | GovConnection | PO-2026-003 | 2028-01-20 | New | Deployed | Maria Santos | 2026-02-15 | Employee Home
AST-014 | CAC-002 | CAC Reader | HID Omnikey 3121 | HID-N5O6P7 | 2026-01-20 | 34.99 | GovConnection | PO-2026-003 | 2028-01-20 | New | Deployed | James Carter | 2026-02-16 | Employee Home
AST-015 | CAC-003 | CAC Reader | HID Omnikey 3121 | HID-Q8R9S1 | 2026-01-20 | 34.99 | GovConnection | PO-2026-003 | 2028-01-20 | New | Configured |  |  | Warehouse
AST-016 | KBM-001 | Keyboard/Mouse | Logitech MK540 | LOG-T2U3V4 | 2026-01-25 | 49.99 | Amazon Business | PO-2026-004 | 2028-01-25 | New | Deployed | Maria Santos | 2026-02-15 | Employee Home
AST-017 | KBM-002 | Keyboard/Mouse | Logitech MK540 | LOG-W5X6Y7 | 2026-01-25 | 49.99 | Amazon Business | PO-2026-004 | 2028-01-25 | New | Deployed | James Carter | 2026-02-16 | Employee Home
AST-018 | WBC-001 | Webcam | Logitech C920s | LOGC-Z8A1B2 | 2026-02-05 | 69.99 | Amazon Business | PO-2026-006 | 2028-02-05 | New | Deployed | Maria Santos | 2026-02-15 | Employee Home
AST-019 | WBC-002 | Webcam | Logitech C920s | LOGC-C3D4E5 | 2026-02-05 | 69.99 | Amazon Business | PO-2026-006 | 2028-02-05 | New | Shipped |  |  | In Transit
AST-020 | DOC-001 | Docking Station | Dell WD22TB4 | DWD-F6G7H8 | 2026-01-12 | 279.99 | Dell Technologies | PO-2026-001 | 2029-01-12 | New | Deployed | Aisha Johnson | 2026-01-20 | Employee Home
AST-021 | DOC-002 | Docking Station | Dell WD22TB4 | DWD-I9J1K2 | 2026-01-12 | 279.99 | Dell Technologies | PO-2026-001 | 2029-01-12 | New | In Stock |  |  | Warehouse
AST-022 | MPH-001 | Mobile Phone | iPhone 15 | APL-L3M4N5 | 2025-12-01 | 999 | Apple Business | PO-2025-050 | 2027-12-01 | Good | Deployed | Robert Chen | 2026-01-05 | Employee Home | Supervisor device
AST-023 | PRT-001 | Printer | HP LaserJet Pro M404n | HPP-O6P7Q8 | 2025-06-15 | 349 | HP Inc. | PO-2025-022 | 2026-06-15 | Fair | Deployed | Sarah Williams | 2025-08-01 | Employee Home | Toner replacement needed
AST-024 | SWL-001 | Software License | Microsoft 365 E3 | MS365-R9S1T2 | 2026-01-01 | 432 | Microsoft | PO-2026-010 | 2027-01-01 | New | Deployed | Maria Santos | 2026-01-15 | Employee Home | Annual license
AST-025 | LPT-006 | Laptop | Dell Latitude 5540 | DL5540-U3V4W5 | 2026-03-01 | 1249.99 | Dell Technologies | PO-2026-015 | 2029-03-01 | New | In Stock |  |  | Warehouse | Reserve unit

## Procurement Tracker
Request ID | Request Date | Requested By | Equipment Type | Quantity | Unit Cost | Total Cost | Vendor | PO Number | Order Date | Expected Delivery | Actual Delivery | Status | Approval Status | Approved By | Tracking Number | Carrier | Days to Fulfill | Notes
REQ-001 | 2026-01-05 | Kelly Thompson | Laptop | 10 | 1249.99 |  | Dell Technologies | PO-2026-001 | 2026-01-08 | 2026-01-20 | 2026-01-18 | Received | Approved | Mike Davis | 1Z999AA10123456784 | UPS |  | Bulk order for surge
REQ-002 | 2026-01-10 | Kelly Thompson | Monitor | 10 | 489.99 |  | Dell Technologies | PO-2026-002 | 2026-01-12 | 2026-01-25 | 2026-01-24 | Received | Approved | Mike Davis | 1Z999AA10123456785 | UPS |  | 27-inch monitors
REQ-003 | 2026-01-12 | Kelly Thompson | CAC Reader | 20 | 34.99 |  | GovConnection | PO-2026-003 | 2026-01-14 | 2026-01-22 | 2026-01-21 | Received | Approved | Mike Davis | 9400111899223100001 | USPS
REQ-004 | 2026-01-15 | Kelly Thompson | Keyboard/Mouse | 15 | 49.99 |  | Amazon Business | PO-2026-004 | 2026-01-16 | 2026-01-23 | 2026-01-22 | Received | Approved | Mike Davis | TBA612345678901 | FedEx |  | Wireless combo sets
REQ-005 | 2026-01-20 | Sarah Williams | Headset | 15 | 229.99 |  | Jabra Direct | PO-2026-005 | 2026-01-22 | 2026-02-03 | 2026-02-01 | Received | Approved | Mike Davis | 1Z999AA10123456786 | UPS
REQ-006 | 2026-01-25 | Sarah Williams | Webcam | 10 | 69.99 |  | Amazon Business | PO-2026-006 | 2026-01-27 | 2026-02-05 | 2026-02-04 | Received | Approved | Mike Davis | TBA612345678902 | FedEx
REQ-007 | 2026-02-01 | Kelly Thompson | Docking Station | 8 | 279.99 |  | Dell Technologies | PO-2026-007 | 2026-02-03 | 2026-02-15 | 2026-02-14 | Received | Approved | Mike Davis | 1Z999AA10123456787 | UPS
REQ-008 | 2026-02-10 | Sarah Williams | Laptop | 5 | 1249.99 |  | Dell Technologies | PO-2026-008 | 2026-02-12 | 2026-02-25 | 2026-02-24 | Received | Approved | Mike Davis | 1Z999AA10123456788 | UPS |  | Second wave hiring
REQ-009 | 2026-02-20 | Kelly Thompson | Monitor | 5 | 449 |  | CDW | PO-2026-009 | 2026-02-22 | 2026-03-05 | 2026-03-04 | Received | Approved | Mike Davis | 1Z999AA10123456789 | UPS |  | LG monitors
REQ-010 | 2026-03-01 | Kelly Thompson | Laptop | 10 | 1249.99 |  | Dell Technologies | PO-2026-015 | 2026-03-03 | 2026-03-15 | 2026-03-14 | Received | Approved | Mike Davis | 1Z999AA10123456790 | UPS |  | Third wave
REQ-011 | 2026-03-10 | Sarah Williams | Headset | 10 | 199.99 |  | CDW | PO-2026-016 | 2026-03-12 | 2026-03-22 |  | Shipped | Approved | Mike Davis | 1Z999AA10123456791 | UPS |  | Poly headsets
REQ-012 | 2026-03-15 | Kelly Thompson | Docking Station | 5 | 279.99 |  | Dell Technologies | PO-2026-017 | 2026-03-17 | 2026-03-28 |  | Ordered | Approved | Mike Davis |  | FedEx
REQ-013 | 2026-04-01 | Sarah Williams | Laptop | 8 | 1189 |  | HP Inc. | PO-2026-020 | 2026-04-03 | 2026-04-18 |  | Shipped | Approved | Mike Davis | 774820135792468 | DHL |  | HP EliteBooks
REQ-014 | 2026-04-10 | Kelly Thompson | Webcam | 10 | 69.99 |  | Amazon Business |  |  |  |  | Requested | Pending |  |  |  |  | Awaiting approval
REQ-015 | 2026-04-15 | Sarah Williams | Mobile Phone | 3 | 999 |  | Apple Business |  |  |  |  | Requested | Pending |  |  |  |  | Supervisor phones

## Deployment Tracker
Employee Name | Employee ID | Position | Start Date | Kit Type | Laptop Asset ID | Monitor Asset ID | Headset Asset ID | CAC Reader Asset ID | Other Equipment | Kit Status | Ship Date | Tracking Number | Carrier | Expected Delivery | Actual Delivery | Delivery Confirmed By | Remote Workspace Verified | VPN Configured | All Software Installed | Overall Readiness | Days to Deploy | Notes
Maria Santos | EMP-1001 | Claims Examiner | 2026-02-17 | Standard Remote Kit | AST-001 | AST-006 | AST-010 | AST-013 | KBM-001, WBC-001 | Verified | 2026-02-10 | 1Z999AA10100001 | UPS | 2026-02-14 | 2026-02-13 | Maria Santos | Yes | Yes | Yes | Ready
James Carter | EMP-1002 | Claims Examiner | 2026-02-17 | Standard Remote Kit | AST-002 | AST-007 | AST-011 | AST-014 | KBM-002 | Verified | 2026-02-10 | 1Z999AA10100002 | UPS | 2026-02-14 | 2026-02-14 | James Carter | Yes | Yes | Yes | Ready
Aisha Johnson | EMP-1003 | Senior Claims Examiner | 2026-01-27 | Enhanced Remote Kit | AST-004 |  | AST-011 | AST-013 | DOC-001 | Verified | 2026-01-18 | 1Z999AA10100003 | UPS | 2026-01-22 | 2026-01-21 | Aisha Johnson | Yes | Yes | Yes | Ready
David Kim | EMP-1004 | Claims Examiner | 2026-01-27 | Standard Remote Kit | AST-005 | AST-009 |  | CAC-003 |  | Verified | 2026-01-20 | 1Z999AA10100004 | UPS | 2026-01-24 | 2026-01-23 | David Kim | Yes | Yes | Yes | Ready |  | Separating 4/30
Robert Chen | EMP-1005 | Supervisor | 2026-01-12 | Supervisor Kit | AST-004 | AST-008 | AST-012 | CAC-002 | MPH-001, DOC-002 | Verified | 2026-01-06 | 1Z999AA10100005 | FedEx | 2026-01-10 | 2026-01-09 | Robert Chen | Yes | Yes | Yes | Ready
Sarah Williams | EMP-1006 | IT Support Lead | 2025-08-01 | Enhanced Remote Kit | AST-004 | AST-008 | AST-012 | CAC-003 | PRT-001 | Verified | 2025-07-25 | 1Z999AA10100006 | UPS | 2025-07-30 | 2025-07-29 | Sarah Williams | Yes | Yes | Yes | Ready
Lisa Park | EMP-1007 | Claims Examiner | 2026-03-02 | Standard Remote Kit | AST-025 |  |  |  |  | Shipped | 2026-02-25 | 1Z999AA10100007 | UPS | 2026-03-01 |  |  | Pending | Pending | Pending | Not Ready |  | Awaiting delivery
Michael Brown | EMP-1008 | Claims Examiner | 2026-03-02 | Standard Remote Kit | [5 empty] | Assembling | [6 empty] | Pending | No | No | Not Ready |  | Kit being assembled
Jennifer Liu | EMP-1009 | Claims Examiner | 2026-03-09 | Standard Remote Kit | [5 empty] | Not Started | [6 empty] | Pending | No | No | Not Ready |  | New hire wave 3
Carlos Rodriguez | EMP-1010 | Claims Examiner | 2026-03-09 | Standard Remote Kit | [5 empty] | Not Started | [6 empty] | Pending | No | No | Not Ready |  | New hire wave 3
Emma Thompson | EMP-1011 | Senior Claims Examiner | 2026-03-16 | Enhanced Remote Kit | [5 empty] | Not Started | [6 empty] | No | No | No | Not Ready
Ahmed Hassan | EMP-1012 | Claims Examiner | 2026-03-16 | Standard Remote Kit | [5 empty] | Not Started | [6 empty] | Pending | No | No | Not Ready
Rachel Green | EMP-1013 | Claims Examiner | 2026-03-23 | Standard Remote Kit | [5 empty] | Not Started | [6 empty] | Pending | No | No | Not Ready
Tom Reed | EMP-1014 | Claims Examiner | 2026-01-15 | Standard Remote Kit | AST-005 | AST-009 | AST-012 | CAC-003 |  | Verified | 2026-01-08 | 1Z999AA10100014 | UPS | 2026-01-12 | 2026-01-12 | Tom Reed | Yes | Yes | Yes | Ready |  | Separated 3/15
Nina Patel | EMP-1015 | Claims Examiner | 2026-03-30 | Standard Remote Kit | [5 empty] | Not Started | [6 empty] | Pending | No | No | Not Ready
Brian Scott | EMP-1016 | Supervisor | 2026-04-06 | Supervisor Kit | [5 empty] | Not Started | [6 empty] | No | No | No | Not Ready
Diana Foster | EMP-1017 | Claims Examiner | 2026-04-06 | Standard Remote Kit | [5 empty] | Not Started | [6 empty] | Pending | No | No | Not Ready
Kevin Wright | EMP-1018 | Claims Examiner | 2026-04-13 | Standard Remote Kit | [5 empty] | Not Started | [6 empty] | Pending | No | No | Not Ready
Laura Martinez | EMP-1019 | Senior Claims Examiner | 2026-04-13 | Enhanced Remote Kit | [5 empty] | Not Started | [6 empty] | No | No | No | Not Ready
Jason Lee | EMP-1020 | Claims Examiner | 2026-04-20 | Standard Remote Kit | [5 empty] | Not Started | [6 empty] | Pending | No | No | Not Ready |  | Starting today

## Return Tracker
Employee Name | Employee ID | Separation Date | Return Initiated Date | Return Deadline | Assets to Return | Return Kit Sent | Return Shipping Label Sent | Tracking Number | Carrier | Return Received Date | Assets Received | Assets Missing | Condition on Return | Financial Liability | Liability Amount | Status | Days Overdue | Escalation Notes
Tom Reed | EMP-1014 | 2026-03-15 | 2026-03-16 | 2026-03-30 | AST-005, AST-009, AST-012, CAC-003 | Yes | Yes | 1Z999AA10200001 | UPS | 2026-03-28 | AST-005, AST-009, AST-012, CAC-003 |  | Good | None | 0 | Complete
David Kim | EMP-1004 | 2026-04-30 | 2026-04-15 | 2026-05-14 | AST-005, AST-009, CAC-003 | Yes | Yes | [6 empty] | None | 0 | Pending |  | Pre-separation initiated
Angela White | EMP-0998 | 2026-02-28 | 2026-03-01 | 2026-03-14 | LPT-010, MON-005, HDS-004 | Yes | Yes | 1Z999AA10200002 | UPS | 2026-03-20 | LPT-010, MON-005 | HDS-004 | Fair | Partial | 229.99 | Escalated |  | Headset not returned - payroll deduction initiated
Marcus Jones | EMP-0995 | 2026-01-31 | 2026-02-01 | 2026-02-14 | LPT-008, MON-006, HDS-005, CAC-004 | Yes | Yes | 1Z999AA10200003 | FedEx | 2026-02-12 | LPT-008, MON-006, HDS-005, CAC-004 |  | Good | None | 0 | Complete
Patricia Clark | EMP-0990 | 2026-03-07 | 2026-03-08 | 2026-03-21 | LPT-009, MON-007, HDS-006, CAC-005, DOC-003 | Yes | Yes | 1Z999AA10200004 | UPS |  |  |  |  | None | 0 | Escalated |  | Package lost in transit - claim filed with UPS
Steven Wright | EMP-0988 | 2026-04-10 | 2026-04-11 | 2026-04-25 | LPT-011, MON-008, HDS-007 | Yes | Yes | 1Z999AA10200005 | FedEx |  |  |  |  | None | 0 | In Transit |  | Tracking shows in transit
Nancy Taylor | EMP-0985 | 2026-03-20 | 2026-03-21 | 2026-04-03 | LPT-012, MON-009, HDS-008, CAC-006 | Yes | Yes | 9400111899223100005 | USPS | 2026-04-08 | LPT-012, MON-009, CAC-006 | HDS-008 | Damaged | Full | 199.99 | Escalated |  | Laptop screen cracked - full liability assessed
George Adams | EMP-0982 | 2026-04-05 | 2026-04-06 | 2026-04-19 | LPT-013, MON-010, HDS-009, CAC-007 | No | No | [6 empty] | None | 0 | Pending |  | Return kit not yet sent - awaiting address confirmation
Formulas:
Days Overdue = IF([Status]="Complete",0,IF([Status]="Written Off",0,IF([Return Received Date]<>"",0,IF(TODAY()>[Return Deadline],TODAY()-[Return Deadline],0))))

## Remote Workspace Checklist
Employee Name | Employee ID | Dedicated Workspace | Adequate Lighting | Reliable Internet - Min 25 Mbps | Speed Test Result | Backup Internet Plan | Surge Protector | Ergonomic Setup | Private/Secure Location | Photo Submitted | Verification Date | Verified By | Overall Status | Notes
Maria Santos | EMP-1001 | Yes | Yes | Yes | 85 Mbps | No | Yes | Yes | Yes | Yes | 2026-02-14 | Sarah Williams | Approved
James Carter | EMP-1002 | Yes | Yes | Yes | 120 Mbps | Yes | Yes | Yes | Yes | Yes | 2026-02-14 | Sarah Williams | Approved
Aisha Johnson | EMP-1003 | Yes | Yes | Yes | 200 Mbps | Yes | Yes | Yes | Yes | Yes | 2026-01-19 | Sarah Williams | Approved | Fiber connection
David Kim | EMP-1004 | Yes | Yes | Yes | 75 Mbps | No | Yes | Pending | Yes | Yes | 2026-01-19 | Sarah Williams | Conditional | Ergonomic assessment pending
Robert Chen | EMP-1005 | Yes | Yes | Yes | 150 Mbps | Yes | Yes | Yes | Yes | Yes | 2026-01-08 | Sarah Williams | Approved | Home office setup
Sarah Williams | EMP-1006 | Yes | Yes | Yes | 300 Mbps | Yes | Yes | Yes | Yes | Yes | 2025-07-28 | Mike Davis | Approved
Lisa Park | EMP-1007 | Yes | Yes | Yes | 50 Mbps | No | Yes | Pending | Yes | No |  |  | Pending Review | Photo not yet submitted
Michael Brown | EMP-1008 | Pending | Pending | Pending |  | Pending | Pending | Pending | Pending | No |  |  | Pending Review | Not yet assessed
Jennifer Liu | EMP-1009 | Pending | Pending | Pending |  | Pending | Pending | Pending | Pending | No |  |  | Pending Review | New hire - wave 3
Carlos Rodriguez | EMP-1010 | Yes | Yes | No | 18 Mbps | No | No | Pending | Yes | Yes | 2026-03-05 | Sarah Williams | Not Approved | Internet speed below minimum - needs upgrade
Emma Thompson | EMP-1011 | Pending | Pending | Pending |  | Pending | Pending | Pending | Pending | No |  |  | Pending Review
Ahmed Hassan | EMP-1012 | Yes | Yes | Yes | 95 Mbps | No | Yes | Yes | Yes | Yes | 2026-03-12 | Sarah Williams | Approved
Rachel Green | EMP-1013 | Pending | Pending | Pending |  | Pending | Pending | Pending | Pending | No |  |  | Pending Review
Tom Reed | EMP-1014 | Yes | Yes | Yes | 60 Mbps | No | Yes | Yes | Yes | Yes | 2026-01-10 | Sarah Williams | Approved | Separated 3/15
Nina Patel | EMP-1015 | Pending | Pending | Pending |  | Pending | Pending | Pending | Pending | No |  |  | Pending Review
Brian Scott | EMP-1016 | Pending | Pending | Pending |  | Pending | Pending | Pending | Pending | No |  |  | Pending Review
Diana Foster | EMP-1017 | Yes | Yes | Yes | 110 Mbps | Yes | Pending | Pending | Yes | No |  |  | Pending Review | Internet verified, other items pending
Kevin Wright | EMP-1018 | Pending | Pending | Pending |  | Pending | Pending | Pending | Pending | No |  |  | Pending Review
Laura Martinez | EMP-1019 | Yes | No | Yes | 45 Mbps | No | Yes | No | Yes | Yes | 2026-04-10 | Sarah Williams | Conditional | Lighting and ergonomic issues noted
Jason Lee | EMP-1020 | Pending | Pending | Pending |  | Pending | Pending | Pending | Pending | No |  |  | Pending Review | Starting 4/20

## Alerts
Alert Type | Priority | Description | Related Asset/Employee | Date Flagged | Status | Assigned To | Resolution Notes
Overdue Returns | High | Return package lost in transit - UPS claim filed | Patricia Clark (EMP-0990) | 2026-03-25 | Open | Sarah Williams | UPS investigating - claim #CLM-887421
Missing Equipment | High | Headset not returned with separation kit | Angela White (EMP-0998) / HDS-004 | 2026-03-22 | In Progress | Kelly Thompson | Payroll deduction initiated for $229.99
Warranty Expiring | Medium | Monitor warranty expiring within 90 days | AST-009 (LG 27UK850-W) | 2026-04-15 | Open | Sarah Williams
Unfulfilled Deployments | High | Kit assembly not started - start date approaching | Michael Brown (EMP-1008) | 2026-04-10 | Open | Kelly Thompson | Start date 3/2 - significantly overdue
Workspace Not Verified | Medium | Internet speed below 25 Mbps minimum | Carlos Rodriguez (EMP-1010) | 2026-03-06 | Open | Sarah Williams | Employee notified - ISP upgrade in progress
Procurement Delays | Medium | Docking station order placed but no tracking yet | REQ-012 / PO-2026-017 | 2026-04-05 | Open | Kelly Thompson | Contacted Dell for status update
Damaged Equipment | High | Laptop returned with cracked screen | Nancy Taylor (EMP-0985) / LPT-012 | 2026-04-09 | In Progress | Sarah Williams | Full liability assessed - $1,249.99
Lost Assets | High | Return shipment lost - 4 assets unaccounted for | Patricia Clark (EMP-0990) | 2026-04-01 | Open | Kelly Thompson | Insurance claim pending
Unfulfilled Deployments | Medium | 10 employees in wave 3-4 have no kit assignment | EMP-1009 through EMP-1020 | 2026-04-15 | Open | Kelly Thompson | Pending procurement REQ-013, REQ-014
Overdue Returns | Medium | Return kit not sent - awaiting address confirmation | George Adams (EMP-0982) | 2026-04-12 | Open | Sarah Williams | HR contacted for updated address
Warranty Expiring | Low | Printer warranty expiring within 90 days | AST-023 (HP LaserJet Pro) | 2026-04-15 | Open | Sarah Williams
Procurement Delays | Medium | Two procurement requests pending approval for 10+ days | REQ-014, REQ-015 | 2026-04-20 | Open | Mike Davis | Escalated to contracting officer