## Training Dashboard
TRAINING CURRICULUM MATRIX — DASHBOARD
Last Updated: | 2026-04-20
Total Training Modules | Overall Completion Rate | Modules On Track | Modules Behind Schedule | Modules Not Started | Average Assessment Score | Certifications Current | Certifications Expiring (30 days) | Failed Assessments Requiring Retake
30 | 72% | 22 | 5 | 3 | 84% | 32 | 5 | 4
COMPLETION RATE BY CATEGORY |  |  |  | COMPLETION BY ROLE
Category | Completion Rate | Status |  | Role | Headcount | Avg Modules Required | Avg Completed | % Complete
Security & Compliance | 85% | On Track |  | Agent | 12 | 22 | 15 | 68%
Systems & Technology | 78% | On Track |  | Senior Agent | 3 | 26 | 22 | 85%
Operations & Processes | 70% | Caution |  | Team Lead | 2 | 24 | 19 | 79%
Customer Service | 65% | Caution |  | Supervisor | 1 | 24 | 21 | 88%
Quality Assurance | 60% | Caution |  | QA Analyst | 2 | 20 | 16 | 80%
Leadership & Supervision | 55% | Behind
TRAINING PHASE STATUS | [5 empty] | ALERT SUMMARY
Training Phase | % Complete | Status | Target Date | Notes |  | Alert Type | Count | Severity
Phase 1 — Pre-Boarding | 100% | Complete | 2026-04-30 | All modules delivered |  | Overdue Trainings | 2 | High
Phase 2 — Orientation | 90% | On Track | 2026-05-08 | 2 employees catching up |  | Expiring Certifications | 5 | Medium
Phase 3 — Core Training | 70% | In Progress | 2026-05-15 | Key modules in delivery |  | Failed Assessments | 4 | High
Phase 4 — Specialized | 50% | In Progress | 2026-05-22 | Starting Week 4 |  | Modules Behind Schedule | 2 | Medium
Phase 5 — OJT | 30% | Scheduled | 2026-05-29 | Begins Week 5 |  | Material Updates Required | 1 | Low
KEY
≥ 80% | On Track / Good | 60-79% | Caution / Monitor | < 60% | Behind / At Risk

## Curriculum Master List
Module ID | Module Name | Category | Training Phase | Description | Learning Objectives | Delivery Method | Duration (hrs) | Prerequisites | Required For | Assessment Type | Passing Score (%) | Recurrence | Materials/Resources | SME/Instructor | Priority | Status
TRN-001 | CUI Handling & Marking | Security & Compliance | Phase 1 Pre-Boarding | Training on proper handling, marking, and safeguarding of Controlled Unclassified Information | Identify CUI categories; Apply correct markings; Follow dissemination controls | eLearning | 2 | None | All Staff | Quiz | 90 | Annual | CUI Marking Handbook, NARA CUI Registry | J. Morrison | Critical | Active
TRN-002 | NIST 800-171 Security Awareness | Security & Compliance | Phase 1 Pre-Boarding | Overview of NIST 800-171 security requirements for protecting CUI in nonfederal systems | Understand NIST 800-171 families; Identify security controls; Report compliance gaps | eLearning | 1.5 | None | All Staff | Quiz | 85 | Annual | NIST SP 800-171 Rev 2, Security Policy Manual | J. Morrison | Critical | Active
TRN-003 | PII Protection | Security & Compliance | Phase 1 Pre-Boarding | Comprehensive training on identifying, handling, and protecting Personally Identifiable Information | Define PII; Apply privacy safeguards; Respond to PII breaches | eLearning | 1 | None | All Staff | Quiz | 90 | Annual | Privacy Act Overview, PII Handling Guide | S. Chen | Critical | Active
TRN-004 | Insider Threat Awareness | Security & Compliance | Phase 2 Orientation | Recognizing and reporting potential insider threat indicators in a remote work environment | Identify insider threat indicators; Understand reporting channels; Apply behavioral analysis | Virtual Instructor-Led | 2 | TRN-001 | All Staff | Quiz | 80 | Annual | Insider Threat Program Guide, Case Studies | S. Chen | High | Active
TRN-005 | Incident Reporting Procedures | Security & Compliance | Phase 2 Orientation | Procedures for identifying, documenting, and reporting security incidents and data breaches | Follow incident response steps; Document incidents properly; Use reporting tools | Blended | 1.5 | TRN-001, TRN-003 | All Staff | Practical Demo | 85 | Annual | Incident Response Plan, Reporting Templates | S. Chen | High | Active
TRN-006 | Physical Security for Remote Workers | Security & Compliance | Phase 1 Pre-Boarding | Establishing and maintaining a secure remote work environment per contract requirements | Set up secure workspace; Manage visitor access; Secure physical documents | eLearning | 1 | None | All Staff | Quiz | 85 | Annual | Remote Work Security Checklist, Home Office Guide | J. Morrison | High | Active
TRN-007 | VPN & Secure Remote Access Setup | Systems & Technology | Phase 1 Pre-Boarding | Configuration and use of VPN, virtual desktop, and secure remote access tools | Install and configure VPN; Troubleshoot connectivity; Follow access protocols | Virtual Instructor-Led | 2 | TRN-012 | All Staff | Practical Demo | 100 | One-Time | VPN Setup Guide, Network Diagram, Troubleshooting FAQ | M. Patel | Critical | Active
TRN-008 | Case Management System Training | Systems & Technology | Phase 3 Core Training | In-depth training on the case management system used for processing and tracking cases | Navigate CMS interface; Create and update cases; Generate reports; Apply workflow rules | Blended | 8 | TRN-007, TRN-013 | Agents Only | Practical Demo | 80 | One-Time | CMS User Manual, Practice Environment Access | M. Patel | Critical | Active
TRN-009 | Collaboration Tools (Teams/SharePoint) | Systems & Technology | Phase 2 Orientation | Using Microsoft Teams, SharePoint, and other collaboration tools for remote teamwork | Navigate Teams channels; Share documents in SharePoint; Use video conferencing | eLearning | 1.5 | TRN-007 | All Staff | None | N/A | One-Time | Teams Quick Start Guide, SharePoint Navigation Guide | R. Williams | Medium | Active
TRN-010 | Secure Document Management | Systems & Technology | Phase 2 Orientation | Proper handling, storage, and transmission of documents in secure digital environments | Apply document classification; Use encrypted storage; Follow transmission protocols | Virtual Instructor-Led | 2 | TRN-001, TRN-007 | All Staff | Quiz | 80 | Annual | Document Handling SOP, Classification Guide | M. Patel | High | Active
TRN-011 | Reporting & Analytics Tools | Systems & Technology | Phase 4 Specialized | Advanced training on reporting dashboards, analytics tools, and data visualization | Build custom reports; Interpret analytics dashboards; Export data for analysis | Virtual Instructor-Led | 3 | TRN-008, TRN-010 | Team Leads+ | Practical Demo | 80 | One-Time | Analytics Platform User Guide, Report Templates | M. Patel | Medium | Active
TRN-012 | Multi-Factor Authentication & Account Security | Systems & Technology | Phase 1 Pre-Boarding | Setting up MFA, managing credentials, and maintaining account security | Configure MFA; Manage secure passwords; Recognize phishing attempts | eLearning | 0.5 | None | All Staff | Quiz | 100 | Annual | MFA Setup Guide, Password Policy Document | R. Williams | Critical | Active
TRN-013 | Standard Operating Procedures Overview | Operations & Processes | Phase 3 Core Training | Comprehensive review of all standard operating procedures for daily operations | Understand operational workflows; Apply SOPs to daily tasks; Identify process exceptions | Virtual Instructor-Led | 4 | TRN-006, TRN-007 | All Staff | Quiz | 80 | One-Time | SOP Manual, Process Flow Charts, Quick Reference Cards | L. Thompson | Critical | Active
TRN-014 | Workflow & Escalation Procedures | Operations & Processes | Phase 3 Core Training | Understanding case workflows, escalation paths, and exception handling procedures | Follow escalation matrix; Document escalations; Apply priority classifications | Blended | 3 | TRN-013 | All Staff | Practical Demo | 80 | One-Time | Escalation Matrix, Workflow Diagrams | L. Thompson | High | Active
TRN-015 | Time & Attendance Reporting | Operations & Processes | Phase 2 Orientation | Using timekeeping systems, reporting procedures, and leave management | Submit accurate timesheets; Request leave properly; Understand overtime policies | eLearning | 1 | None | All Staff | None | N/A | One-Time | Timesheet Guide, Leave Policy Document | A. Garcia | Medium | Active
TRN-016 | Contract Compliance & SLA Awareness | Operations & Processes | Phase 3 Core Training | Understanding contract requirements, service level agreements, and performance metrics | Identify key SLAs; Monitor performance targets; Report compliance issues | Virtual Instructor-Led | 2 | TRN-013 | All Staff | Quiz | 85 | Semi-Annual | Contract Summary, SLA Dashboard Guide, KPI Definitions | L. Thompson | High | Active
TRN-017 | Records Management & Retention | Operations & Processes | Phase 3 Core Training | Federal records management requirements, retention schedules, and disposal procedures | Apply retention schedules; Manage electronic records; Follow disposal procedures | eLearning | 1.5 | TRN-001, TRN-010 | All Staff | Quiz | 80 | Annual | Records Retention Schedule, NARA Guidelines | A. Garcia | Medium | Active
TRN-018 | Telework Policy & Expectations | Operations & Processes | Phase 1 Pre-Boarding | Remote work policies, expectations, performance standards, and work-life balance | Understand telework agreement; Set up compliant workspace; Follow availability requirements | Self-Paced | 1 | None | All Staff | None | N/A | One-Time | Telework Agreement, Remote Work Policy, FAQ | A. Garcia | High | Active
TRN-019 | Customer Service Excellence | Customer Service | Phase 3 Core Training | Foundational customer service skills for government contact center operations | Apply active listening; Use professional communication; Resolve inquiries efficiently | Virtual Instructor-Led | 4 | TRN-013 | Agents Only | Observation | 80 | One-Time | Customer Service Handbook, Call Scripts, Scenario Library | D. Robinson | High | Active
TRN-020 | Difficult Caller Handling & De-escalation | Customer Service | Phase 4 Specialized | Advanced techniques for managing difficult interactions and de-escalating tense situations | Apply de-escalation techniques; Manage emotional callers; Know when to escalate | Virtual Instructor-Led | 3 | TRN-019 | Agents Only | Practical Demo | 80 | Semi-Annual | De-escalation Guide, Role-Play Scenarios | D. Robinson | High | Active
TRN-021 | Communication Standards & Etiquette | Customer Service | Phase 3 Core Training | Professional communication standards for phone, email, and chat interactions | Follow communication templates; Apply tone and language guidelines; Document interactions | Blended | 2 | TRN-013 | Agents Only | Observation | 80 | One-Time | Communication Style Guide, Email Templates, Chat Guidelines | D. Robinson | Medium | Active
TRN-022 | Cultural Sensitivity & Diversity | Customer Service | Phase 2 Orientation | Understanding cultural differences and providing inclusive service to diverse populations | Recognize cultural differences; Apply inclusive language; Accommodate diverse needs | eLearning | 1.5 | None | All Staff | Quiz | 80 | Annual | Diversity & Inclusion Guide, Cultural Competency Resources | D. Robinson | Medium | Active
TRN-023 | Quality Standards & Expectations | Quality Assurance | Phase 3 Core Training | Overview of quality standards, evaluation criteria, and performance expectations | Understand quality scorecard; Apply evaluation criteria; Self-assess performance | Virtual Instructor-Led | 3 | TRN-013, TRN-016 | All Staff | Quiz | 85 | One-Time | Quality Scorecard, Evaluation Rubric, Sample Evaluations | K. Nguyen | High | Active
TRN-024 | QA Monitoring & Calibration | Quality Assurance | Phase 4 Specialized | Advanced QA monitoring techniques, calibration sessions, and inter-rater reliability | Conduct quality evaluations; Participate in calibration; Ensure scoring consistency | Blended | 4 | TRN-023 | QA Only | Practical Demo | 85 | Quarterly | QA Monitoring Guide, Calibration Schedule, Scoring Matrix | K. Nguyen | Critical | Active
TRN-025 | Self-Assessment & Continuous Improvement | Quality Assurance | Phase 4 Specialized | Tools and techniques for self-evaluation and continuous professional improvement | Use self-assessment tools; Create improvement plans; Track progress metrics | Self-Paced | 1.5 | TRN-023 | All Staff | None | N/A | One-Time | Self-Assessment Template, Improvement Plan Worksheet | K. Nguyen | Medium | Active
TRN-026 | Root Cause Analysis | Quality Assurance | Phase 4 Specialized | Methodologies for identifying root causes of quality issues and process failures | Apply RCA methodologies; Document findings; Recommend corrective actions | Virtual Instructor-Led | 2 | TRN-023, TRN-014 | Team Leads+ | Practical Demo | 80 | One-Time | RCA Toolkit, Fishbone Diagram Templates, Case Studies | K. Nguyen | Medium | Active
TRN-027 | Remote Team Leadership | Leadership & Supervision | Phase 4 Specialized | Leading and managing remote teams effectively in a government contract environment | Apply remote leadership strategies; Build team engagement; Manage virtual meetings | Virtual Instructor-Led | 4 | TRN-013, TRN-009 | Supervisors Only | Observation | 80 | One-Time | Remote Leadership Playbook, Engagement Toolkit | P. Anderson | High | Active
TRN-028 | Performance Management & Coaching | Leadership & Supervision | Phase 4 Specialized | Performance evaluation, coaching techniques, and employee development planning | Conduct performance reviews; Apply coaching frameworks; Create development plans | Blended | 3 | TRN-027 | Team Leads+ | Practical Demo | 80 | Annual | Performance Management Guide, Coaching Models, Review Templates | P. Anderson | High | Active
TRN-029 | Conflict Resolution & Employee Relations | Leadership & Supervision | Phase 4 Specialized | Managing workplace conflicts and maintaining positive employee relations remotely | Apply conflict resolution models; Mediate disputes; Document employee issues | Virtual Instructor-Led | 2 | TRN-027 | Team Leads+ | Observation | 80 | Annual | Conflict Resolution Framework, ER Case Studies, Documentation Templates | P. Anderson | Medium | Active
TRN-030 | Workforce Planning & Surge Management | Leadership & Supervision | Phase 4 Specialized | Planning and executing workforce surges for government contract operations | Develop surge plans; Manage rapid onboarding; Optimize staffing models | Virtual Instructor-Led | 3 | TRN-027, TRN-016 | Supervisors Only | Quiz | 85 | One-Time | Surge Planning Template, Staffing Models, Lessons Learned | P. Anderson | High | Active

## Training Schedule
Week | Day | Date | Phase | Time Block | Module ID | Module Name | Delivery Method | Duration (hrs) | Instructor/Facilitator | Target Audience | Location/Platform | Prerequisites Completed? | Notes
1 | Monday | 2026-04-27 | Phase 1 Pre-Boarding | 9:00 AM - 11:00 AM | TRN-012 | Multi-Factor Authentication & Account Security | eLearning | 0.5 | R. Williams | All Staff | LMS Portal | Yes | Complete before VPN setup
1 | Monday | 2026-04-27 | Phase 1 Pre-Boarding | 11:00 AM - 1:00 PM | TRN-007 | VPN & Secure Remote Access Setup | Virtual Instructor-Led | 2 | M. Patel | All Staff | MS Teams | Yes | Hands-on lab included
1 | Monday | 2026-04-27 | Phase 1 Pre-Boarding | 2:00 PM - 3:00 PM | TRN-018 | Telework Policy & Expectations | Self-Paced | 1 | A. Garcia | All Staff | LMS Portal | Yes | Review telework agreement
1 | Tuesday | 2026-04-28 | Phase 1 Pre-Boarding | 9:00 AM - 11:00 AM | TRN-001 | CUI Handling & Marking | eLearning | 2 | J. Morrison | All Staff | LMS Portal | Yes | Critical — required for subsequent modules
1 | Tuesday | 2026-04-28 | Phase 1 Pre-Boarding | 11:00 AM - 12:00 PM | TRN-003 | PII Protection | eLearning | 1 | S. Chen | All Staff | LMS Portal | Yes
1 | Tuesday | 2026-04-28 | Phase 1 Pre-Boarding | 1:00 PM - 2:30 PM | TRN-002 | NIST 800-171 Security Awareness | eLearning | 1.5 | J. Morrison | All Staff | LMS Portal | Yes
1 | Wednesday | 2026-04-29 | Phase 1 Pre-Boarding | 9:00 AM - 10:00 AM | TRN-006 | Physical Security for Remote Workers | eLearning | 1 | J. Morrison | All Staff | LMS Portal | Yes | Home office setup verification
1 | Wednesday | 2026-04-29 | Phase 2 Orientation | 10:30 AM - 12:30 PM | TRN-004 | Insider Threat Awareness | Virtual Instructor-Led | 2 | S. Chen | All Staff | MS Teams | Yes | Interactive case studies
1 | Thursday | 2026-04-30 | Phase 2 Orientation | 9:00 AM - 10:30 AM | TRN-005 | Incident Reporting Procedures | Blended | 1.5 | S. Chen | All Staff | MS Teams + LMS | Yes | Practical demo component
1 | Thursday | 2026-04-30 | Phase 2 Orientation | 11:00 AM - 12:30 PM | TRN-022 | Cultural Sensitivity & Diversity | eLearning | 1.5 | D. Robinson | All Staff | LMS Portal | Yes
1 | Friday | 2026-05-01 | Phase 2 Orientation | 9:00 AM - 11:00 AM | TRN-010 | Secure Document Management | Virtual Instructor-Led | 2 | M. Patel | All Staff | MS Teams | Yes
1 | Friday | 2026-05-01 | Phase 2 Orientation | 11:30 AM - 1:00 PM | TRN-009 | Collaboration Tools (Teams/SharePoint) | eLearning | 1.5 | R. Williams | All Staff | LMS Portal | Yes | Hands-on practice session
2 | Monday | 2026-05-04 | Phase 2 Orientation | 9:00 AM - 10:00 AM | TRN-015 | Time & Attendance Reporting | eLearning | 1 | A. Garcia | All Staff | LMS Portal | Yes | Submit first timesheet by EOD
2 | Monday | 2026-05-04 | Phase 3 Core Training | 10:30 AM - 2:30 PM | TRN-013 | Standard Operating Procedures Overview | Virtual Instructor-Led | 4 | L. Thompson | All Staff | MS Teams | Yes | Full-day session with breaks
2 | Tuesday | 2026-05-05 | Phase 3 Core Training | 9:00 AM - 12:00 PM | TRN-014 | Workflow & Escalation Procedures | Blended | 3 | L. Thompson | All Staff | MS Teams + LMS | Yes | Includes escalation role-play
2 | Tuesday | 2026-05-05 | Phase 3 Core Training | 1:00 PM - 3:00 PM | TRN-016 | Contract Compliance & SLA Awareness | Virtual Instructor-Led | 2 | L. Thompson | All Staff | MS Teams | Yes
2 | Wednesday | 2026-05-06 | Phase 3 Core Training | 9:00 AM - 10:30 AM | TRN-017 | Records Management & Retention | eLearning | 1.5 | A. Garcia | All Staff | LMS Portal | Yes
2 | Wednesday | 2026-05-06 | Phase 3 Core Training | 11:00 AM - 2:00 PM | TRN-023 | Quality Standards & Expectations | Virtual Instructor-Led | 3 | K. Nguyen | All Staff | MS Teams | Yes | Review quality scorecard
2 | Thursday | 2026-05-07 | Phase 3 Core Training | 9:00 AM - 5:00 PM | TRN-008 | Case Management System Training | Blended | 8 | M. Patel | Agents Only | MS Teams + CMS Sandbox | Yes | Full-day hands-on lab
2 | Friday | 2026-05-08 | Phase 3 Core Training | 9:00 AM - 1:00 PM | TRN-019 | Customer Service Excellence | Virtual Instructor-Led | 4 | D. Robinson | Agents Only | MS Teams | Yes | Role-play scenarios included
3 | Monday | 2026-05-11 | Phase 3 Core Training | 9:00 AM - 11:00 AM | TRN-021 | Communication Standards & Etiquette | Blended | 2 | D. Robinson | Agents Only | MS Teams + LMS | Yes | Email and chat practice
3 | Monday | 2026-05-11 | Phase 3 Core Training | 1:00 PM - 3:00 PM | TRN-008 | Case Management System Training (Day 2) | Blended | 2 | M. Patel | Agents Only | CMS Sandbox | Yes | Advanced CMS exercises
3 | Tuesday | 2026-05-12 | Phase 3 Core Training | 9:00 AM - 12:00 PM | TRN-008 | Case Management System Training (Day 3) | Blended | 3 | M. Patel | Agents Only | CMS Sandbox | Yes | Assessment prep
3 | Tuesday | 2026-05-12 | Phase 3 Core Training | 1:00 PM - 3:00 PM | TRN-016 | Contract Compliance & SLA Review | Virtual Instructor-Led | 2 | L. Thompson | All Staff | MS Teams | Yes | Refresher for mid-cycle
3 | Wednesday | 2026-05-13 | Phase 3 Core Training | 9:00 AM - 12:00 PM | TRN-008 | CMS Practical Assessment | Blended | 3 | M. Patel | Agents Only | CMS Sandbox | Yes | Practical demo assessment
3 | Wednesday | 2026-05-13 | Phase 3 Core Training | 1:00 PM - 4:00 PM | TRN-023 | Quality Standards Review & Quiz | Virtual Instructor-Led | 3 | K. Nguyen | All Staff | MS Teams | Yes | Assessment day
3 | Thursday | 2026-05-14 | Phase 3 Core Training | 9:00 AM - 1:00 PM | TRN-019 | Customer Service — Advanced Scenarios | Virtual Instructor-Led | 4 | D. Robinson | Agents Only | MS Teams | Yes | Observation assessment
3 | Friday | 2026-05-15 | Phase 3 Core Training | 9:00 AM - 12:00 PM |  | Phase 3 Assessments & Remediation |  | 3 | All Instructors | All Staff | MS Teams + LMS | Yes | Retakes and catch-up
4 | Monday | 2026-05-18 | Phase 4 Specialized | 9:00 AM - 12:00 PM | TRN-020 | Difficult Caller Handling & De-escalation | Virtual Instructor-Led | 3 | D. Robinson | Agents Only | MS Teams | Yes | Advanced role-play
4 | Monday | 2026-05-18 | Phase 4 Specialized | 1:00 PM - 4:00 PM | TRN-011 | Reporting & Analytics Tools | Virtual Instructor-Led | 3 | M. Patel | Team Leads+ | MS Teams | Yes | Dashboard lab session
4 | Tuesday | 2026-05-19 | Phase 4 Specialized | 9:00 AM - 1:00 PM | TRN-024 | QA Monitoring & Calibration | Blended | 4 | K. Nguyen | QA Only | MS Teams + QA Tools | Yes | Calibration exercise
4 | Tuesday | 2026-05-19 | Phase 4 Specialized | 9:00 AM - 11:00 AM | TRN-026 | Root Cause Analysis | Virtual Instructor-Led | 2 | K. Nguyen | Team Leads+ | MS Teams | Yes | Concurrent session
4 | Wednesday | 2026-05-20 | Phase 4 Specialized | 9:00 AM - 10:30 AM | TRN-025 | Self-Assessment & Continuous Improvement | Self-Paced | 1.5 | K. Nguyen | All Staff | LMS Portal | Yes
4 | Wednesday | 2026-05-20 | Phase 4 Specialized | 11:00 AM - 3:00 PM | TRN-027 | Remote Team Leadership | Virtual Instructor-Led | 4 | P. Anderson | Supervisors Only | MS Teams | Yes
4 | Thursday | 2026-05-21 | Phase 4 Specialized | 9:00 AM - 12:00 PM | TRN-028 | Performance Management & Coaching | Blended | 3 | P. Anderson | Team Leads+ | MS Teams + LMS | Yes | Coaching practice lab
4 | Friday | 2026-05-22 | Phase 4 Specialized | 9:00 AM - 11:00 AM | TRN-029 | Conflict Resolution & Employee Relations | Virtual Instructor-Led | 2 | P. Anderson | Team Leads+ | MS Teams | Yes | Case study analysis
4 | Friday | 2026-05-22 | Phase 4 Specialized | 11:30 AM - 2:30 PM | TRN-030 | Workforce Planning & Surge Management | Virtual Instructor-Led | 3 | P. Anderson | Supervisors Only | MS Teams | Yes
5 | Monday | 2026-05-25 | Phase 5 OJT | 9:00 AM - 5:00 PM |  | OJT Day 1 — Shadowing | On-the-Job | 8 | Assigned Mentor | All Staff | Virtual Shadow | Yes | Paired with experienced agent
5 | Tuesday | 2026-05-26 | Phase 5 OJT | 9:00 AM - 5:00 PM |  | OJT Day 2 — Assisted Calls | On-the-Job | 8 | Assigned Mentor | Agents Only | Production Environment | Yes | Mentor monitors in real-time
5 | Wednesday | 2026-05-27 | Phase 5 OJT | 9:00 AM - 5:00 PM |  | OJT Day 3 — Supervised Production | On-the-Job | 8 | Team Lead | Agents Only | Production Environment | Yes | Reduced mentor oversight
5 | Thursday | 2026-05-28 | Phase 5 OJT | 9:00 AM - 5:00 PM |  | OJT Day 4 — Independent Work | On-the-Job | 8 | Team Lead | Agents Only | Production Environment | Yes | QA monitoring active
5 | Friday | 2026-05-29 | Phase 5 OJT | 9:00 AM - 12:00 PM |  | OJT Assessment & Graduation | On-the-Job | 3 | All Instructors | All Staff | MS Teams | Yes | Final evaluations and certification

## Employee Training Tracker
Employee ID | Employee Name | Role | Hire Date | Clearance Status | TRN-001 Status | TRN-001 Date | TRN-001 Score | TRN-002 Status | TRN-002 Date | TRN-002 Score | TRN-003 Status | TRN-003 Date | TRN-003 Score | TRN-004 Status | TRN-004 Date | TRN-004 Score | TRN-005 Status | TRN-005 Date | TRN-005 Score | TRN-006 Status | TRN-006 Date | TRN-006 Score | TRN-007 Status | TRN-007 Date | TRN-007 Score | TRN-008 Status | TRN-008 Date | TRN-008 Score | TRN-009 Status | TRN-009 Date | TRN-009 Score | TRN-010 Status | TRN-010 Date | TRN-010 Score | TRN-011 Status | TRN-011 Date | TRN-011 Score | TRN-012 Status | TRN-012 Date | TRN-012 Score | TRN-013 Status | TRN-013 Date | TRN-013 Score | TRN-014 Status | TRN-014 Date | TRN-014 Score | TRN-015 Status | TRN-015 Date | TRN-015 Score | TRN-016 Status | TRN-016 Date | TRN-016 Score | TRN-017 Status | TRN-017 Date | TRN-017 Score | TRN-018 Status | TRN-018 Date | TRN-018 Score | TRN-019 Status | TRN-019 Date | TRN-019 Score | TRN-020 Status | TRN-020 Date | TRN-020 Score | TRN-021 Status | TRN-021 Date | TRN-021 Score | TRN-022 Status | TRN-022 Date | TRN-022 Score | TRN-023 Status | TRN-023 Date | TRN-023 Score | TRN-024 Status | TRN-024 Date | TRN-024 Score | TRN-025 Status | TRN-025 Date | TRN-025 Score | TRN-026 Status | TRN-026 Date | TRN-026 Score | TRN-027 Status | TRN-027 Date | TRN-027 Score | TRN-028 Status | TRN-028 Date | TRN-028 Score | TRN-029 Status | TRN-029 Date | TRN-029 Score | TRN-030 Status | TRN-030 Date | TRN-030 Score | Total Modules Required | Modules Completed | Completion % | Average Score | On Track
EMP-001 | Marcus J. Washington | Agent | 2026-03-02 | Final | Completed | 2026-03-05 | 95 | Completed | 2026-03-05 | 90 | Completed | 2026-03-04 | 92 | Completed | 2026-03-10 | 85 | Completed | 2026-03-10 | 88 | Completed | 2026-03-04 | 90 | Completed | 2026-03-03 | 100 | Completed | 2026-03-18 | 85 | Completed | 2026-03-11 |  | Completed | 2026-03-11 | 82 | Exempt |  |  | Completed | 2026-03-03 | 100 | Completed | 2026-03-16 | 84 | Completed | 2026-03-17 | 82 | Completed | 2026-03-09 |  | Completed | 2026-03-18 | 88 | Completed | 2026-03-19 | 80 | Completed | 2026-03-03 |  | Completed | 2026-03-20 | 83 | Completed | 2026-04-01 | 82 | Completed | 2026-03-20 | 80 | Completed | 2026-03-09 | 85 | Completed | 2026-03-19 | 87 | Exempt |  |  | Completed | 2026-04-02 |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt
EMP-002 | Sarah L. Mitchell | Agent | 2026-03-02 | Final | Completed | 2026-03-05 | 92 | Completed | 2026-03-05 | 88 | Completed | 2026-03-04 | 94 | Completed | 2026-03-10 | 82 | Completed | 2026-03-11 | 86 | Completed | 2026-03-04 | 88 | Completed | 2026-03-03 | 100 | Completed | 2026-03-19 | 82 | Completed | 2026-03-11 |  | Completed | 2026-03-11 | 80 | Exempt |  |  | Completed | 2026-03-03 | 100 | Completed | 2026-03-16 | 80 | Completed | 2026-03-17 | 84 | Completed | 2026-03-09 |  | Completed | 2026-03-18 | 86 | In Progress |  |  | Completed | 2026-03-03 |  | Completed | 2026-03-21 | 85 | In Progress |  |  | Completed | 2026-03-21 | 82 | Completed | 2026-03-09 | 80 | Completed | 2026-03-20 | 86 | Exempt |  |  | In Progress |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt
EMP-003 | David R. Hernandez | Senior Agent | 2026-03-02 | Final | Completed | 2026-03-04 | 96 | Completed | 2026-03-04 | 92 | Completed | 2026-03-04 | 95 | Completed | 2026-03-09 | 88 | Completed | 2026-03-10 | 90 | Completed | 2026-03-04 | 92 | Completed | 2026-03-03 | 100 | Completed | 2026-03-17 | 88 | Completed | 2026-03-09 |  | Completed | 2026-03-10 | 85 | Completed | 2026-04-06 | 84 | Completed | 2026-03-03 | 100 | Completed | 2026-03-15 | 86 | Completed | 2026-03-16 | 85 | Completed | 2026-03-09 |  | Completed | 2026-03-17 | 90 | Completed | 2026-03-18 | 82 | Completed | 2026-03-03 |  | Completed | 2026-03-19 | 88 | Completed | 2026-03-30 | 85 | Completed | 2026-03-19 | 84 | Completed | 2026-03-09 | 82 | Completed | 2026-03-18 | 90 | Exempt |  |  | Completed | 2026-04-02 |  | Completed | 2026-04-07 | 82 | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt
EMP-004 | Jennifer A. Collins | Team Lead | 2026-03-09 | Final | Completed | 2026-03-11 | 94 | Completed | 2026-03-11 | 90 | Completed | 2026-03-10 | 92 | Completed | 2026-03-16 | 86 | Completed | 2026-03-17 | 88 | Completed | 2026-03-10 | 90 | Completed | 2026-03-09 | 100 | Exempt |  |  | Completed | 2026-03-16 |  | Completed | 2026-03-17 | 84 | Completed | 2026-04-08 | 82 | Completed | 2026-03-09 | 100 | Completed | 2026-03-23 | 88 | Completed | 2026-03-24 | 86 | Completed | 2026-03-15 |  | Completed | 2026-03-25 | 90 | Completed | 2026-03-26 | 84 | Completed | 2026-03-09 |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Completed | 2026-03-16 | 84 | Completed | 2026-03-26 | 88 | Exempt |  |  | Completed | 2026-04-09 |  | Completed | 2026-04-10 | 84 | Exempt |  |  | Completed | 2026-04-13 | 82 | Completed | 2026-04-14 | 80 | Exempt
EMP-005 | Robert T. Kim | Agent | 2026-03-09 | Final | Completed | 2026-03-12 | 90 | Completed | 2026-03-12 | 86 | Completed | 2026-03-11 | 88 | Completed | 2026-03-17 | 80 | Completed | 2026-03-18 | 82 | Completed | 2026-03-11 | 86 | Completed | 2026-03-10 | 100 | Completed | 2026-03-25 | 80 | Completed | 2026-03-17 |  | Completed | 2026-03-18 | 82 | Exempt |  |  | Completed | 2026-03-10 | 100 | Completed | 2026-03-23 | 82 | Completed | 2026-03-24 | 80 | Completed | 2026-03-16 |  | Completed | 2026-03-25 | 85 | In Progress |  |  | Completed | 2026-03-10 |  | Completed | 2026-03-27 | 80 | In Progress |  |  | In Progress |  |  | Completed | 2026-03-16 | 80 | In Progress |  |  | Exempt |  |  | Not Started |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt
EMP-006 | Amanda K. Brooks | QA Analyst | 2026-03-09 | Final | Completed | 2026-03-12 | 94 | Completed | 2026-03-12 | 90 | Completed | 2026-03-11 | 92 | Completed | 2026-03-16 | 84 | Completed | 2026-03-17 | 88 | Completed | 2026-03-11 | 88 | Completed | 2026-03-10 | 100 | Exempt |  |  | Completed | 2026-03-16 |  | Completed | 2026-03-17 | 84 | Exempt |  |  | Completed | 2026-03-10 | 100 | Completed | 2026-03-23 | 86 | Completed | 2026-03-24 | 84 | Completed | 2026-03-15 |  | Completed | 2026-03-25 | 88 | Completed | 2026-03-26 | 82 | Completed | 2026-03-10 |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Completed | 2026-03-16 | 82 | Completed | 2026-03-26 | 88 | Completed | 2026-04-08 | 90 | In Progress |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt
EMP-007 | Michael D. Torres | Supervisor | 2026-03-09 | Final | Completed | 2026-03-10 | 98 | Completed | 2026-03-10 | 94 | Completed | 2026-03-10 | 96 | Completed | 2026-03-16 | 90 | Completed | 2026-03-16 | 92 | Completed | 2026-03-10 | 94 | Completed | 2026-03-09 | 100 | Exempt |  |  | Completed | 2026-03-15 |  | Completed | 2026-03-16 | 88 | Completed | 2026-04-06 | 86 | Completed | 2026-03-09 | 100 | Completed | 2026-03-22 | 90 | Completed | 2026-03-23 | 88 | Completed | 2026-03-14 |  | Completed | 2026-03-24 | 92 | Completed | 2026-03-25 | 86 | Completed | 2026-03-09 |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Completed | 2026-03-15 | 86 | Completed | 2026-03-25 | 90 | Exempt |  |  | Completed | 2026-04-07 |  | Completed | 2026-04-08 | 86 | Completed | 2026-04-10 | 82 | Completed | 2026-04-13 | 85 | In Progress |  |  | Completed | 2026-04-15 | 88
EMP-008 | Lisa M. Patel | Agent | 2026-03-16 | Final | Completed | 2026-03-18 | 90 | Completed | 2026-03-18 | 85 | Completed | 2026-03-17 | 88 | Completed | 2026-03-23 | 80 | Completed | 2026-03-24 | 82 | Completed | 2026-03-17 | 85 | Completed | 2026-03-16 | 100 | Completed | 2026-04-01 | 78 | Completed | 2026-03-23 |  | Completed | 2026-03-24 | 80 | Exempt |  |  | Completed | 2026-03-16 | 100 | Completed | 2026-03-30 | 80 | Completed | 2026-03-31 | 80 | Completed | 2026-03-22 |  | In Progress |  |  | Not Started |  |  | Completed | 2026-03-16 |  | Completed | 2026-04-03 | 80 | Not Started |  |  | In Progress |  |  | Completed | 2026-03-23 | 80 | In Progress |  |  | Exempt |  |  | Not Started |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt
EMP-009 | James W. O'Brien | Agent | 2026-03-16 | Interim | Completed | 2026-03-19 | 88 | Completed | 2026-03-19 | 82 | Completed | 2026-03-18 | 86 | Completed | 2026-03-24 | 78 | Failed | 2026-03-25 | 70 | Completed | 2026-03-18 | 84 | Completed | 2026-03-17 | 100 | In Progress |  |  | Completed | 2026-03-24 |  | Completed | 2026-03-25 | 80 | Exempt |  |  | Completed | 2026-03-17 | 100 | Completed | 2026-04-01 | 78 | In Progress |  |  | Completed | 2026-03-23 |  | Not Started |  |  | Not Started |  |  | Completed | 2026-03-17 |  | In Progress |  |  | Not Started |  |  | Not Started |  |  | Completed | 2026-03-24 | 78 | Not Started |  |  | Exempt |  |  | Not Started |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt
EMP-010 | Crystal N. Davis | Senior Agent | 2026-03-16 | Final | Completed | 2026-03-18 | 94 | Completed | 2026-03-18 | 90 | Completed | 2026-03-17 | 92 | Completed | 2026-03-23 | 86 | Completed | 2026-03-24 | 88 | Completed | 2026-03-17 | 90 | Completed | 2026-03-16 | 100 | Completed | 2026-03-31 | 84 | Completed | 2026-03-23 |  | Completed | 2026-03-24 | 85 | Completed | 2026-04-10 | 82 | Completed | 2026-03-16 | 100 | Completed | 2026-03-30 | 85 | Completed | 2026-03-31 | 84 | Completed | 2026-03-22 |  | Completed | 2026-04-01 | 88 | In Progress |  |  | Completed | 2026-03-16 |  | Completed | 2026-04-03 | 85 | In Progress |  |  | Completed | 2026-04-03 | 82 | Completed | 2026-03-23 | 84 | Completed | 2026-04-02 | 86 | Exempt |  |  | In Progress |  |  | In Progress |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt
EMP-011 | Anthony F. Nguyen | Agent | 2026-03-23 | Interim | Completed | 2026-03-26 | 88 | Completed | 2026-03-26 | 84 | Completed | 2026-03-25 | 86 | Completed | 2026-03-31 | 80 | In Progress |  |  | Completed | 2026-03-25 | 84 | Completed | 2026-03-24 | 100 | In Progress |  |  | Completed | 2026-03-31 |  | In Progress |  |  | Exempt |  |  | Completed | 2026-03-24 | 100 | In Progress |  |  | Not Started |  |  | Completed | 2026-03-30 |  | Not Started |  |  | Not Started |  |  | Completed | 2026-03-24 |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | In Progress |  |  | Not Started |  |  | Exempt |  |  | Not Started |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt
EMP-012 | Michelle R. Johnson | Agent | 2026-03-23 | Final | Completed | 2026-03-25 | 90 | Completed | 2026-03-25 | 86 | Completed | 2026-03-24 | 88 | Completed | 2026-03-30 | 82 | Completed | 2026-03-31 | 84 | Completed | 2026-03-24 | 86 | Completed | 2026-03-23 | 100 | In Progress |  |  | Completed | 2026-03-30 |  | Completed | 2026-03-31 | 82 | Exempt |  |  | Completed | 2026-03-23 | 100 | Completed | 2026-04-06 | 82 | In Progress |  |  | Completed | 2026-03-29 |  | Not Started |  |  | Not Started |  |  | Completed | 2026-03-23 |  | In Progress |  |  | Not Started |  |  | Not Started |  |  | Completed | 2026-03-30 | 82 | Not Started |  |  | Exempt |  |  | Not Started |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt
EMP-013 | Kevin S. Williams | Team Lead | 2026-03-23 | Final | Completed | 2026-03-25 | 92 | Completed | 2026-03-25 | 88 | Completed | 2026-03-24 | 90 | Completed | 2026-03-30 | 84 | Completed | 2026-03-31 | 86 | Completed | 2026-03-24 | 88 | Completed | 2026-03-23 | 100 | Exempt |  |  | Completed | 2026-03-30 |  | Completed | 2026-03-31 | 84 | In Progress |  |  | Completed | 2026-03-23 | 100 | Completed | 2026-04-06 | 84 | Completed | 2026-04-07 | 82 | Completed | 2026-03-29 |  | In Progress |  |  | Not Started |  |  | Completed | 2026-03-23 |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Completed | 2026-03-30 | 84 | In Progress |  |  | Exempt |  |  | Not Started |  |  | Not Started |  |  | Exempt |  |  | Not Started |  |  | Not Started |  |  | Exempt
EMP-014 | Stephanie D. Garcia | Agent | 2026-03-30 | Interim | Completed | 2026-04-02 | 86 | Completed | 2026-04-02 | 82 | Completed | 2026-04-01 | 84 | In Progress |  |  | Not Started |  |  | Completed | 2026-04-01 | 82 | Completed | 2026-03-31 | 100 | Not Started |  |  | In Progress |  |  | Not Started |  |  | Exempt |  |  | Completed | 2026-03-31 | 100 | Not Started |  |  | Not Started |  |  | In Progress |  |  | Not Started |  |  | Not Started |  |  | Completed | 2026-03-31 |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Exempt |  |  | Not Started |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt
EMP-015 | Brian E. Thompson | Agent | 2026-03-30 | Interim | Completed | 2026-04-02 | 84 | Completed | 2026-04-02 | 80 | Completed | 2026-04-01 | 82 | In Progress |  |  | Not Started |  |  | Completed | 2026-04-01 | 80 | Completed | 2026-03-31 | 100 | Not Started |  |  | Not Started |  |  | Not Started |  |  | Exempt |  |  | Completed | 2026-03-31 | 100 | Not Started |  |  | Not Started |  |  | In Progress |  |  | Not Started |  |  | Not Started |  |  | Completed | 2026-03-31 |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Exempt |  |  | Not Started |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt
EMP-016 | Rachel A. Lee | QA Analyst | 2026-03-30 | Final | Completed | 2026-04-01 | 92 | Completed | 2026-04-01 | 88 | Completed | 2026-03-31 | 90 | Completed | 2026-04-06 | 84 | In Progress |  |  | Completed | 2026-03-31 | 88 | Completed | 2026-03-30 | 100 | Exempt |  |  | Completed | 2026-04-06 |  | In Progress |  |  | Exempt |  |  | Completed | 2026-03-30 | 100 | In Progress |  |  | Not Started |  |  | Completed | 2026-04-05 |  | Not Started |  |  | Not Started |  |  | Completed | 2026-03-30 |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Completed | 2026-04-06 | 82 | Not Started |  |  | Not Started |  |  | Not Started |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt
EMP-017 | Christopher M. Brown | Agent | 2026-04-06 | Interim | Completed | 2026-04-08 | 86 | Completed | 2026-04-08 | 80 | Completed | 2026-04-07 | 84 | Not Started |  |  | Not Started |  |  | Completed | 2026-04-07 | 82 | Completed | 2026-04-06 | 100 | Not Started |  |  | Not Started |  |  | Not Started |  |  | Exempt |  |  | Completed | 2026-04-06 | 100 | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Completed | 2026-04-06 |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Exempt |  |  | Not Started |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt
EMP-018 | Natalie J. Rivera | Senior Agent | 2026-04-06 | Interim | Completed | 2026-04-08 | 88 | Completed | 2026-04-09 | 84 | Completed | 2026-04-08 | 86 | Not Started |  |  | Not Started |  |  | Completed | 2026-04-08 | 84 | Completed | 2026-04-07 | 100 | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Completed | 2026-04-07 | 100 | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Completed | 2026-04-07 |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Exempt |  |  | Not Started |  |  | Not Started |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt
EMP-019 | Daniel P. Clarke | Agent | 2026-04-13 | Pending | Completed | 2026-04-15 | 82 | Failed | 2026-04-15 | 72 | Completed | 2026-04-14 | 80 | Not Started |  |  | Not Started |  |  | In Progress |  |  | Completed | 2026-04-14 | 100 | Not Started |  |  | Not Started |  |  | Not Started |  |  | Exempt |  |  | Completed | 2026-04-14 | 100 | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | In Progress |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Exempt |  |  | Not Started |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt
EMP-020 | Samantha H. Foster | Agent | 2026-04-13 | Pending | Completed | 2026-04-16 | 80 | In Progress |  |  | In Progress |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Completed | 2026-04-15 | 100 | Not Started |  |  | Not Started |  |  | Not Started |  |  | Exempt |  |  | Completed | 2026-04-15 | 100 | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Exempt |  |  | Not Started |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt |  |  | Exempt

## Certification Tracker
Cert ID | Employee ID | Employee Name | Certification Name | Issuing Body | Category | Date Earned | Expiration Date | Days Until Expiration | Renewal Status | Renewal Requirements | Cost | Funded By | Documentation on File | Notes
CERT-001 | EMP-001 | Marcus J. Washington | Interim Security Clearance | DCSA | Security & Compliance | 2026-03-02 | 2026-09-02 |  | Current | Upgrade to final clearance | 0 | Government | Yes | Interim granted; final investigation pending
CERT-002 | EMP-001 | Marcus J. Washington | CUI Handling Certification | Company | Security & Compliance | 2026-03-05 | 2027-03-05 |  | Current | Complete TRN-001 annually | 0 | Company | Yes
CERT-003 | EMP-002 | Sarah L. Mitchell | Final Security Clearance | DCSA | Security & Compliance | 2026-03-02 | 2031-03-02 |  | Current | Reinvestigation every 5 years | 0 | Government | Yes
CERT-004 | EMP-002 | Sarah L. Mitchell | CUI Handling Certification | Company | Security & Compliance | 2026-03-05 | 2027-03-05 |  | Current | Complete TRN-001 annually | 0 | Company | Yes
CERT-005 | EMP-003 | David R. Hernandez | Final Security Clearance | DCSA | Security & Compliance | 2026-03-02 | 2031-03-02 |  | Current | Reinvestigation every 5 years | 0 | Government | Yes
CERT-006 | EMP-003 | David R. Hernandez | CUI Handling Certification | Company | Security & Compliance | 2026-03-04 | 2027-03-04 |  | Current | Complete TRN-001 annually | 0 | Company | Yes
CERT-007 | EMP-003 | David R. Hernandez | CMS Advanced User Certification | CMS Vendor | Systems & Technology | 2026-04-01 | 2027-04-01 |  | Current | Recertify annually | 150 | Company | Yes
CERT-008 | EMP-004 | Jennifer A. Collins | Final Security Clearance | DCSA | Security & Compliance | 2026-03-09 | 2031-03-09 |  | Current | Reinvestigation every 5 years | 0 | Government | Yes
CERT-009 | EMP-004 | Jennifer A. Collins | CUI Handling Certification | Company | Security & Compliance | 2026-03-11 | 2027-03-11 |  | Current | Complete TRN-001 annually | 0 | Company | Yes
CERT-010 | EMP-004 | Jennifer A. Collins | Project Management Professional | PMI | Leadership & Supervision | 2025-06-15 | 2028-06-15 |  | Current | 60 PDUs every 3 years | 555 | Company | Yes
CERT-011 | EMP-005 | Robert T. Kim | Final Security Clearance | DCSA | Security & Compliance | 2026-03-09 | 2031-03-09 |  | Current | Reinvestigation every 5 years | 0 | Government | Yes
CERT-012 | EMP-005 | Robert T. Kim | CUI Handling Certification | Company | Security & Compliance | 2026-03-12 | 2027-03-12 |  | Current | Complete TRN-001 annually | 0 | Company | Yes
CERT-013 | EMP-006 | Amanda K. Brooks | Final Security Clearance | DCSA | Security & Compliance | 2026-03-09 | 2031-03-09 |  | Current | Reinvestigation every 5 years | 0 | Government | Yes
CERT-014 | EMP-006 | Amanda K. Brooks | Certified Quality Auditor | ASQ | Quality Assurance | 2025-08-20 | 2026-05-10 |  | Expiring Soon | Recertify with 18 RUs | 400 | Company | Pending | Renewal application submitted
CERT-015 | EMP-006 | Amanda K. Brooks | CUI Handling Certification | Company | Security & Compliance | 2026-03-12 | 2027-03-12 |  | Current | Complete TRN-001 annually | 0 | Company | Yes
CERT-016 | EMP-007 | Michael D. Torres | Final Security Clearance | DCSA | Security & Compliance | 2026-03-09 | 2031-03-09 |  | Current | Reinvestigation every 5 years | 0 | Government | Yes
CERT-017 | EMP-007 | Michael D. Torres | CUI Handling Certification | Company | Security & Compliance | 2026-03-10 | 2027-03-10 |  | Current | Complete TRN-001 annually | 0 | Company | Yes
CERT-018 | EMP-007 | Michael D. Torres | SHRM-CP | SHRM | Leadership & Supervision | 2024-11-01 | 2027-11-01 |  | Current | 60 PDCs every 3 years | 375 | Company | Yes
CERT-019 | EMP-008 | Lisa M. Patel | Final Security Clearance | DCSA | Security & Compliance | 2026-03-16 | 2031-03-16 |  | Current | Reinvestigation every 5 years | 0 | Government | Yes
CERT-020 | EMP-008 | Lisa M. Patel | CUI Handling Certification | Company | Security & Compliance | 2026-03-18 | 2027-03-18 |  | Current | Complete TRN-001 annually | 0 | Company | Yes
CERT-021 | EMP-009 | James W. O'Brien | Interim Security Clearance | DCSA | Security & Compliance | 2026-03-16 | 2026-09-16 |  | Current | Upgrade to final clearance | 0 | Government | Yes | Final investigation in progress
CERT-022 | EMP-009 | James W. O'Brien | CUI Handling Certification | Company | Security & Compliance | 2026-03-19 | 2027-03-19 |  | Current | Complete TRN-001 annually | 0 | Company | Yes
CERT-023 | EMP-010 | Crystal N. Davis | Final Security Clearance | DCSA | Security & Compliance | 2026-03-16 | 2031-03-16 |  | Current | Reinvestigation every 5 years | 0 | Government | Yes
CERT-024 | EMP-010 | Crystal N. Davis | CUI Handling Certification | Company | Security & Compliance | 2026-03-18 | 2027-03-18 |  | Current | Complete TRN-001 annually | 0 | Company | Yes
CERT-025 | EMP-010 | Crystal N. Davis | CMS Advanced User Certification | CMS Vendor | Systems & Technology | 2026-04-05 | 2027-04-05 |  | Current | Recertify annually | 150 | Company | Yes
CERT-026 | EMP-011 | Anthony F. Nguyen | Interim Security Clearance | DCSA | Security & Compliance | 2026-03-23 | 2026-09-23 |  | Current | Upgrade to final clearance | 0 | Government | Yes
CERT-027 | EMP-012 | Michelle R. Johnson | Final Security Clearance | DCSA | Security & Compliance | 2026-03-23 | 2031-03-23 |  | Current | Reinvestigation every 5 years | 0 | Government | Yes
CERT-028 | EMP-013 | Kevin S. Williams | Final Security Clearance | DCSA | Security & Compliance | 2026-03-23 | 2031-03-23 |  | Current | Reinvestigation every 5 years | 0 | Government | Yes
CERT-029 | EMP-013 | Kevin S. Williams | Certified Scrum Master | Scrum Alliance | Leadership & Supervision | 2025-01-10 | 2027-01-10 |  | Current | Earn 20 SEUs every 2 years | 250 | Company | Yes
CERT-030 | EMP-014 | Stephanie D. Garcia | Interim Security Clearance | DCSA | Security & Compliance | 2026-03-30 | 2026-09-30 |  | Current | Upgrade to final clearance | 0 | Government | Yes
CERT-031 | EMP-015 | Brian E. Thompson | Interim Security Clearance | DCSA | Security & Compliance | 2026-03-30 | 2026-09-30 |  | Current | Upgrade to final clearance | 0 | Government | Yes
CERT-032 | EMP-016 | Rachel A. Lee | Final Security Clearance | DCSA | Security & Compliance | 2026-03-30 | 2031-03-30 |  | Current | Reinvestigation every 5 years | 0 | Government | Yes
CERT-033 | EMP-016 | Rachel A. Lee | Six Sigma Green Belt | ASQ | Quality Assurance | 2025-04-15 | 2026-04-15 |  | Expired | Recertify with exam or RUs | 350 | Company | No | Renewal overdue — action required
CERT-034 | EMP-017 | Christopher M. Brown | Interim Security Clearance | DCSA | Security & Compliance | 2026-04-06 | 2026-10-06 |  | Current | Upgrade to final clearance | 0 | Government | Pending | Documentation pending
CERT-035 | EMP-018 | Natalie J. Rivera | Interim Security Clearance | DCSA | Security & Compliance | 2026-04-06 | 2026-10-06 |  | Current | Upgrade to final clearance | 0 | Government | Yes
CERT-036 | EMP-018 | Natalie J. Rivera | ITIL Foundation | Axelos | Systems & Technology | 2025-09-20 | 2026-05-20 |  | Expiring Soon | Recertification exam | 300 | Employee | Yes | Exam scheduled for May 2026
CERT-037 | EMP-019 | Daniel P. Clarke | Pending Security Clearance | DCSA | Security & Compliance | 2026-04-13 |  |  | N/A | Awaiting investigation | 0 | Government | Pending | Application submitted
CERT-038 | EMP-020 | Samantha H. Foster | Pending Security Clearance | DCSA | Security & Compliance | 2026-04-13 |  |  | N/A | Awaiting investigation | 0 | Government | Pending | Application submitted
CERT-039 | EMP-007 | Michael D. Torres | CPR/First Aid | American Red Cross | Operations & Processes | 2025-06-01 | 2026-05-01 |  | Expiring Soon | Retake certification course | 75 | Company | Yes | Renewal class scheduled Apr 28
CERT-040 | EMP-004 | Jennifer A. Collins | CPR/First Aid | American Red Cross | Operations & Processes | 2025-05-15 | 2026-05-15 |  | Expiring Soon | Retake certification course | 75 | Company | Yes

## Training Effectiveness
Module ID | Module Name | Category | Total Completions | Average Score | Pass Rate | Avg Time to Complete (hrs) | Student Satisfaction (1-5) | Knowledge Retention Score | On-the-Job Application Rating | Effectiveness Rating | Instructor Rating (1-5) | Recommended Changes | Last Reviewed | Next Review Date
TRN-001 | CUI Handling & Marking | Security & Compliance | 18 | 90.2 | 94% | 1.8 | 4.3 | 88 | 4.2 | Highly Effective | 4.5 | Add more real-world examples | 2026-04-01 | 2026-07-01
TRN-002 | NIST 800-171 Security Awareness | Security & Compliance | 17 | 86.5 | 88% | 1.4 | 3.8 | 82 | 3.9 | Effective | 4.2 | Simplify technical jargon | 2026-04-01 | 2026-07-01
TRN-003 | PII Protection | Security & Compliance | 18 | 88.7 | 94% | 0.9 | 4.5 | 90 | 4.4 | Highly Effective | 4.6 | None — performing well | 2026-04-01 | 2026-07-01
TRN-004 | Insider Threat Awareness | Security & Compliance | 14 | 83.1 | 93% | 1.9 | 4.1 | 80 | 3.8 | Effective | 4.3 | Update case studies to 2026 scenarios | 2026-03-15 | 2026-06-15
TRN-005 | Incident Reporting Procedures | Security & Compliance | 13 | 85.8 | 85% | 1.6 | 3.9 | 78 | 3.7 | Effective | 4 | Add hands-on simulation exercise | 2026-03-15 | 2026-06-15
TRN-006 | Physical Security for Remote Workers | Security & Compliance | 16 | 86.4 | 94% | 0.9 | 4 | 84 | 4.1 | Highly Effective | 4.2 | Include home office photo examples | 2026-04-01 | 2026-07-01
TRN-007 | VPN & Secure Remote Access Setup | Systems & Technology | 18 | 100 | 100% | 2.1 | 4.2 | 95 | 4.6 | Highly Effective | 4.7 | None — critical and well-delivered | 2026-04-01 | 2026-07-01
TRN-008 | Case Management System Training | Systems & Technology | 8 | 82.4 | 88% | 8.5 | 3.6 | 72 | 3.4 | Needs Improvement | 3.8 | Extend lab time; add more practice scenarios | 2026-04-10 | 2026-05-10
TRN-009 | Collaboration Tools (Teams/SharePoint) | Systems & Technology | 14 | 0 | 100% | 1.3 | 4.4 | 85 | 4.3 | Effective | 4.1 | Add SharePoint advanced features section | 2026-03-15 | 2026-06-15
TRN-010 | Secure Document Management | Systems & Technology | 13 | 82.8 | 85% | 2 | 3.7 | 76 | 3.6 | Effective | 3.9 | Provide more classification examples | 2026-03-15 | 2026-06-15
TRN-011 | Reporting & Analytics Tools | Systems & Technology | 4 | 83.5 | 100% | 3.2 | 3.5 | 70 | 3.3 | Needs Improvement | 3.7 | Redesign curriculum for self-paced option | 2026-04-15 | 2026-05-15
TRN-012 | Multi-Factor Authentication & Account Security | Systems & Technology | 18 | 100 | 100% | 0.4 | 4.6 | 96 | 4.7 | Highly Effective | 4.8 | None — streamlined and effective | 2026-04-01 | 2026-07-01
TRN-013 | Standard Operating Procedures Overview | Operations & Processes | 12 | 83.2 | 92% | 4.2 | 3.4 | 74 | 3.5 | Effective | 3.8 | Break into smaller modules | 2026-04-10 | 2026-06-10
TRN-014 | Workflow & Escalation Procedures | Operations & Processes | 10 | 82.6 | 90% | 3.1 | 3.6 | 72 | 3.4 | Needs Improvement | 3.7 | Add more escalation practice scenarios | 2026-04-10 | 2026-06-10
TRN-015 | Time & Attendance Reporting | Operations & Processes | 14 | 0 | 100% | 0.8 | 4.2 | 88 | 4.3 | Effective | 4 | Update screenshots for new timesheet system | 2026-03-15 | 2026-06-15
TRN-016 | Contract Compliance & SLA Awareness | Operations & Processes | 9 | 87.1 | 89% | 2.1 | 3.5 | 76 | 3.5 | Effective | 3.9 | Include more SLA dashboard walkthroughs | 2026-04-10 | 2026-06-10
TRN-017 | Records Management & Retention | Operations & Processes | 6 | 82 | 83% | 1.6 | 3.3 | 68 | 3.2 | Needs Improvement | 3.5 | Modernize content; add interactive elements | 2026-04-10 | 2026-05-10
TRN-018 | Telework Policy & Expectations | Operations & Processes | 16 | 0 | 100% | 0.9 | 4.3 | 90 | 4.5 | Highly Effective | 4.1 | None — self-paced format works well | 2026-04-01 | 2026-07-01
TRN-019 | Customer Service Excellence | Customer Service | 7 | 82.9 | 86% | 4.3 | 3.8 | 74 | 3.6 | Effective | 4.1 | Add more role-play time | 2026-04-10 | 2026-06-10
TRN-020 | Difficult Caller Handling & De-escalation | Customer Service | 3 | 82.3 | 100% | 3.2 | 4 | 70 | 3.4 | Effective | 4.2 | Expand scenario library | 2026-04-15 | 2026-05-15
TRN-021 | Communication Standards & Etiquette | Customer Service | 5 | 81.6 | 100% | 2.1 | 3.4 | 68 | 3.3 | Needs Improvement | 3.6 | Add email/chat writing exercises | 2026-04-10 | 2026-06-10
TRN-022 | Cultural Sensitivity & Diversity | Customer Service | 13 | 82 | 92% | 1.4 | 3.9 | 80 | 3.8 | Effective | 4 | Update with recent DEI best practices | 2026-03-15 | 2026-06-15
TRN-023 | Quality Standards & Expectations | Quality Assurance | 9 | 87 | 89% | 3.1 | 3.7 | 76 | 3.6 | Effective | 4 | Include sample scored evaluations | 2026-04-10 | 2026-06-10
TRN-024 | QA Monitoring & Calibration | Quality Assurance | 2 | 90 | 100% | 4.1 | 4.1 | 82 | 4 | Effective | 4.3 | Schedule more frequent calibration | 2026-04-15 | 2026-05-15
TRN-025 | Self-Assessment & Continuous Improvement | Quality Assurance | 3 | 0 | 100% | 1.4 | 3.2 | 64 | 3 | Needs Improvement | 3.4 | Redesign self-assessment rubric; add examples | 2026-04-15 | 2026-05-15
TRN-026 | Root Cause Analysis | Quality Assurance | 2 | 83 | 100% | 2.2 | 3.8 | 74 | 3.5 | Effective | 3.9 | Add more industry-specific case studies | 2026-04-15 | 2026-06-15
TRN-027 | Remote Team Leadership | Leadership & Supervision | 1 | 82 | 100% | 4.2 | 3.9 | 72 | 3.5 | Effective | 4.1 | Add peer learning component | 2026-04-15 | 2026-06-15
TRN-028 | Performance Management & Coaching | Leadership & Supervision | 2 | 83.5 | 100% | 3.1 | 3.7 | 70 | 3.4 | Needs Improvement | 3.8 | Include more coaching simulations | 2026-04-15 | 2026-05-15
TRN-029 | Conflict Resolution & Employee Relations | Leadership & Supervision | 1 | 80 | 100% | 2.1 | 3.6 | 68 | 3.3 | Needs Improvement | 3.7 | Expand to cover remote-specific conflicts | 2026-04-15 | 2026-05-15
TRN-030 | Workforce Planning & Surge Management | Leadership & Supervision | 1 | 88 | 100% | 3.2 | 4 | 76 | 3.7 | Effective | 4.2 | Include lessons from current surge | 2026-04-15 | 2026-06-15

## Alerts
Alert ID | Date Generated | Alert Type | Employee/Module | Description | Severity | Assigned To | Status | Resolution Date | Notes
ALT-001 | 2026-04-15 | Training Overdue | EMP-009 / TRN-005 | James O'Brien failed Incident Reporting Procedures assessment (score: 70%). Retake required within 14 days. | Critical | S. Chen | Open |  | Scheduled for retake Apr 22
ALT-002 | 2026-04-15 | Certification Expiring | EMP-016 / CERT-033 | Rachel Lee's Six Sigma Green Belt expired on 2026-04-15. Renewal action required. | Critical | K. Nguyen | Acknowledged |  | Renewal application pending
ALT-003 | 2026-04-10 | Certification Expiring | EMP-006 / CERT-014 | Amanda Brooks' Certified Quality Auditor expires 2026-05-10 (20 days). Renewal application submitted. | High | K. Nguyen | Acknowledged |  | Application under review by ASQ
ALT-004 | 2026-04-12 | Certification Expiring | EMP-007 / CERT-039 | Michael Torres' CPR/First Aid expires 2026-05-01 (11 days). Renewal class scheduled. | High | P. Anderson | Acknowledged |  | Class on Apr 28
ALT-005 | 2026-04-12 | Certification Expiring | EMP-004 / CERT-040 | Jennifer Collins' CPR/First Aid expires 2026-05-15 (25 days). | Medium | P. Anderson | Open |  | Needs to register for renewal class
ALT-006 | 2026-04-14 | Certification Expiring | EMP-018 / CERT-036 | Natalie Rivera's ITIL Foundation expires 2026-05-20 (30 days). Exam scheduled. | Medium | M. Patel | Acknowledged |  | Exam on May 18
ALT-007 | 2026-04-18 | Assessment Failed | EMP-019 / TRN-002 | Daniel Clarke failed NIST 800-171 Security Awareness (score: 72%). Minimum passing: 85%. | High | J. Morrison | Open |  | Schedule retake within 10 days
ALT-008 | 2026-04-16 | Module Behind Schedule | TRN-008 | Case Management System Training behind schedule — only 8 of 12 agents completed. Target: all agents by Apr 20. | High | M. Patel | Open |  | 4 agents need to complete
ALT-009 | 2026-04-17 | Training Overdue | EMP-017 / Multiple | Christopher Brown has completed only 8 of 22 required modules. Hired Apr 6 — significantly behind peers. | High | L. Thompson | Open |  | Schedule catch-up training plan
ALT-010 | 2026-04-18 | Material Update Required | TRN-017 | Records Management & Retention module content outdated. Knowledge retention score: 68%. Needs modernization. | Medium | A. Garcia | Open |  | Content review meeting scheduled Apr 23
ALT-011 | 2026-04-19 | Module Behind Schedule | TRN-021 | Communication Standards & Etiquette — only 5 of 12 agents completed. Phase 3 target deadline approaching. | Medium | D. Robinson | Open |  | Prioritize in Week 4 schedule
ALT-012 | 2026-04-20 | Assessment Failed | EMP-008 / TRN-008 | Lisa Patel scored 78% on Case Management System practical demo. Minimum passing: 80%. Retake needed. | High | M. Patel | Open |  | Near-miss — schedule targeted review session