## Command Dashboard
SURGE COMMAND CENTER
Executive Dashboard — Updated 20 April 2026 15:54 CDT
HEADCOUNT | PIPELINE ACTIVE | CLEARANCES COMPLETE |  |  | EQUIP FULFILLED |  |  | TRAINING COMPLETE
Target: 35 | Candidates in Funnel | Of 15 Tracked |  |  | Delivered & Verified |  |  | Personnel Trained
QA AVG SCORE | ATTRITION RATE | OPEN RISKS |  |  | CHECKLIST DONE |  |  | ALERTS OPEN
Across All Monitored | Separations / Hired | Active Risk Items |  |  | Tasks Complete % |  |  | Action Items Pending
PIPELINE FUNNEL DATA | CLEARANCE STATUS DATA | HEADCOUNT RAMP-UP |  |  |  | RISK HEAT MAP DATA
Sourced | Complete | Week | Actual | Target |  | Risk Level | Count | Avg Score | Max Score
Screened | Investigation | Pre-Surge | 3 | 3 |  | Critical
Interviewed | Submitted | Week 1 | 10 | 12 |  | High
Offered | Interim Pending | Week 2 | 18 | 20 |  | Medium
Accepted | Account Created | Week 3 | 25 | 28 |  | Low
Onboarding | Not Started | Week 4 (Plan) | 32 | 35
Deployed
QA SCORE DISTRIBUTION
90-100 (Excellent)
80-89 (Good)
70-79 (Needs Improvement)
Below 70 (Failing)

## Surge Checklist
SURGE CHECKLIST — Day 0-30 Task Tracker
Phase | Task # | Section | Task Description | Owner | Due Date | Completion Date | Status | Priority | Dependencies | Notes
Pre-Surge | T-001 | Workforce Planning | Finalize surge headcount requirements and labor categories | Program Manager | 2026-04-01 | 2026-04-01 | Complete | Critical
Pre-Surge | T-002 | Workforce Planning | Submit staffing plan to contracting officer for approval | Program Manager | 2026-04-02 | 2026-04-02 | Complete | Critical | T-001
Pre-Surge | T-003 | Workforce Planning | Define remote work policies and telework agreements | HR Manager | 2026-04-03 | 2026-04-03 | Complete | High
Pre-Surge | T-004 | Recruiting | Post all surge positions on approved job boards | Recruiting Lead | 2026-04-03 | 2026-04-03 | Complete | Critical | T-001
Pre-Surge | T-005 | Recruiting | Activate staffing agency contracts for contingent hiring | Recruiting Lead | 2026-04-04 | 2026-04-04 | Complete | High
Pre-Surge | T-006 | Security & Compliance | Submit SAAR forms for all anticipated system access | FSO/Security | 2026-04-05 | 2026-04-04 | Complete | Critical
Pre-Surge | T-007 | IT & Equipment | Order laptops and peripherals for first cohort (20 units) | IT Lead | 2026-04-05 | 2026-04-05 | Complete | Critical | T-001
Pre-Surge | T-008 | IT & Equipment | Provision VPN accounts and MFA tokens | IT Lead | 2026-04-06 | 2026-04-06 | Complete | Critical
Pre-Surge | T-009 | Training | Develop virtual training curriculum and LMS modules | Training Lead | 2026-04-06 | 2026-04-05 | Complete | High
Pre-Surge | T-010 | HR & Onboarding | Prepare onboarding packets and welcome emails | HR Manager | 2026-04-07 | 2026-04-07 | Complete | Medium
Day 0-1 | T-011 | Recruiting | Screen and schedule phone interviews for first cohort | Recruiting Lead | 2026-04-08 | 2026-04-08 | Complete | Critical | T-004
Day 0-1 | T-012 | Security & Compliance | Initiate eQIP accounts for cleared positions | FSO/Security | 2026-04-08 | 2026-04-08 | Complete | Critical
Day 0-1 | T-013 | IT & Equipment | Ship equipment to first cohort remote locations | IT Lead | 2026-04-09 | 2026-04-09 | Complete | Critical | T-007
Day 0-1 | T-014 | HR & Onboarding | Conduct virtual Day 1 orientation sessions | HR Manager | 2026-04-09 | 2026-04-09 | Complete | High | T-010
Day 0-1 | T-015 | Training | Launch online security awareness training | Training Lead | 2026-04-09 | 2026-04-08 | Complete | Critical | T-009
Day 2-3 | T-016 | Recruiting | Complete first-round interviews for Cohort 1 | Recruiting Lead | 2026-04-10 | 2026-04-10 | Complete | High | T-011
Day 2-3 | T-017 | Security & Compliance | Collect OF-306 forms from all new hires | FSO/Security | 2026-04-10 | 2026-04-10 | Complete | Critical
Day 2-3 | T-018 | IT & Equipment | Verify remote workspace attestation forms | IT Lead | 2026-04-11 | 2026-04-11 | Complete | High | T-013
Day 2-3 | T-019 | Training | Begin role-specific virtual training modules | Training Lead | 2026-04-11 | 2026-04-11 | Complete | High | T-015
Day 2-3 | T-020 | Quality | Establish QA monitoring schedule and rubrics | QA Lead | 2026-04-11 | 2026-04-10 | Complete | High
Day 4-7 | T-021 | Recruiting | Extend offers to qualified Cohort 1 candidates | Recruiting Lead | 2026-04-13 | 2026-04-12 | Complete | Critical | T-016
Day 4-7 | T-022 | Security & Compliance | Schedule fingerprint appointments for all new hires | FSO/Security | 2026-04-13 | 2026-04-13 | Complete | High | T-017
Day 4-7 | T-023 | IT & Equipment | Confirm VPN connectivity for all deployed staff | IT Lead | 2026-04-14 | 2026-04-14 | Complete | Critical | T-008
Day 4-7 | T-024 | Training | Administer training knowledge checks | Training Lead | 2026-04-14 | 2026-04-14 | Complete | Medium | T-019
Day 4-7 | T-025 | HR & Onboarding | Complete I-9 verification for all new hires | HR Manager | 2026-04-14 | 2026-04-13 | Complete | Critical
Day 4-7 | T-026 | Quality | Conduct first round of live QA monitoring | QA Lead | 2026-04-15 | 2026-04-15 | Complete | High | T-020
Day 4-7 | T-027 | Workforce Planning | Review ramp progress against staffing plan | Program Manager | 2026-04-15 | 2026-04-15 | Complete | High
Week 2 | T-028 | Recruiting | Source and screen Cohort 2 candidates | Recruiting Lead | 2026-04-17 | 2026-04-17 | Complete | High
Week 2 | T-029 | Security & Compliance | Submit interim clearance requests for priority roles | FSO/Security | 2026-04-17 | 2026-04-17 | Complete | Critical | T-012
Week 2 | T-030 | IT & Equipment | Order equipment for Cohort 2 (15 units) | IT Lead | 2026-04-18 | 2026-04-18 | Complete | High
Week 2 | T-031 | Training | Transition Cohort 1 from training to nesting | Training Lead | 2026-04-18 | 2026-04-18 | Complete | High | T-024
Week 2 | T-032 | HR & Onboarding | Conduct 7-day check-in surveys for Cohort 1 | HR Manager | 2026-04-19 | 2026-04-19 | Complete | Medium
Week 2 | T-033 | Quality | Calibrate QA scoring across evaluators | QA Lead | 2026-04-19 |  | In Progress | High | T-026
Week 2 | T-034 | Workforce Planning | Update attrition risk assessment | Program Manager | 2026-04-20 |  | In Progress | Medium
Week 3-4 | T-035 | Recruiting | Complete interviews and offers for Cohort 2 | Recruiting Lead | 2026-04-24 |  | In Progress | High | T-028
Week 3-4 | T-036 | Security & Compliance | Track eQIP submission compliance — target 100% | FSO/Security | 2026-04-24 |  | In Progress | Critical | T-029
Week 3-4 | T-037 | IT & Equipment | Ship and verify equipment for Cohort 2 | IT Lead | 2026-04-25 |  | Not Started | High | T-030
Week 3-4 | T-038 | Training | Begin Cohort 2 virtual training | Training Lead | 2026-04-25 |  | Not Started | High | T-035
Week 3-4 | T-039 | HR & Onboarding | Conduct 30-day check-ins for Cohort 1 | HR Manager | 2026-05-01 |  | Not Started | Medium
Week 3-4 | T-040 | Quality | Publish first QA trend report to leadership | QA Lead | 2026-05-01 |  | Not Started | High | T-033
Week 3-4 | T-041 | Workforce Planning | Prepare surge progress briefing for COR | Program Manager | 2026-05-02 |  | Not Started | Critical | T-034
Week 3-4 | T-042 | Security & Compliance | Conduct CUI handling spot checks for remote staff | FSO/Security | 2026-05-03 |  | Not Started | High
Week 3-4 | T-043 | IT & Equipment | Audit endpoint protection compliance across fleet | IT Lead | 2026-05-03 |  | Not Started | Medium
Week 3-4 | T-044 | Quality | Implement coaching plans for below-threshold performers | QA Lead | 2026-05-04 |  | Not Started | High | T-040
Week 3-4 | T-045 | HR & Onboarding | Process multi-state tax withholding registrations | HR Manager | 2026-05-05 |  | Not Started | Medium

## Candidate Pipeline
CANDIDATE PIPELINE
Candidate ID | First Name | Last Name | Source | Date Sourced | Position Title | Labor Category | Clearance Required | Recruiter | Phone Screen Date | Phone Screen Result | Interview Date | Interviewer(s) | Interview Score | Interview Result | Offer Extended Date | Offer Amount | Offer Accepted | Offer Accept Date | Background Check Status | Drug Test Status | Start Date | Pipeline Stage | Days in Current Stage | Withdrawal Reason | Notes
C-001 | Maria | Santos | Job Board | 2026-03-25 | Case Analyst | Analyst | Public Trust | J. Rivera | 2026-03-27 | Pass | 2026-03-30 | T. Washington | 4.2 | Pass | 2026-04-02 | 72000 | Y | 2026-04-03 | Clear | Pass | 2026-04-09 | Deployed
C-002 | James | Mitchell | Referral | 2026-03-26 | Program Support | Admin | Public Trust | S. Patel | 2026-03-28 | Pass | 2026-03-31 | L. Chen | 3.8 | Pass | 2026-04-03 | 65000 | Y | 2026-04-04 | Clear | Pass | 2026-04-10 | Deployed
C-003 | Aisha | Johnson | Staffing Agency | 2026-03-27 | IT Support Spec | IT | Secret | J. Rivera | 2026-03-29 | Pass | 2026-04-01 | M. Kim | 4.5 | Pass | 2026-04-04 | 85000 | Y | 2026-04-05 | Clear | Pass | 2026-04-11 | Deployed
C-004 | Robert | Williams | Database | 2026-03-28 | Sr. Analyst | Analyst | Secret | S. Patel | 2026-03-30 | Pass | 2026-04-02 | T. Washington | 4 | Pass | 2026-04-05 | 92000 | Y | 2026-04-06 | Pending | Pass | 2026-04-14 | Onboarding |  |  | Awaiting clearance
C-005 | Priya | Sharma | Job Board | 2026-03-29 | Data Entry Clerk | Admin | Public Trust | J. Rivera | 2026-03-31 | Pass | 2026-04-03 | L. Chen | 3.5 | Pass | 2026-04-06 | 55000 | Y | 2026-04-07 | Clear | Pass | 2026-04-13 | Deployed
C-006 | David | Thompson | Internal | 2026-03-30 | QA Specialist | Quality | Public Trust | S. Patel | 2026-04-01 | Pass | 2026-04-04 | M. Kim | 4.3 | Pass | 2026-04-07 | 78000 | Y | 2026-04-08 | Clear | Pass | 2026-04-14 | Deployed
C-007 | Sarah | Brown | Referral | 2026-04-01 | Case Analyst | Analyst | Public Trust | J. Rivera | 2026-04-03 | Pass | 2026-04-07 | T. Washington | 3.9 | Pass | 2026-04-10 | 72000 | Y | 2026-04-11 | Pending | Scheduled | 2026-04-20 | Onboarding
C-008 | Michael | Davis | Job Board | 2026-04-02 | Security Analyst | Security | TS | S. Patel | 2026-04-04 | Pass | 2026-04-08 | L. Chen | 4.7 | Pass | 2026-04-11 | 98000 | Y | 2026-04-12 | Submitted | Pass |  | Accepted |  |  | Clearance pending
C-009 | Jennifer | Garcia | Staffing Agency | 2026-04-03 | Program Support | Admin | Public Trust | J. Rivera | 2026-04-05 | Pass | 2026-04-09 | M. Kim | 3.6 | Pass | 2026-04-12 | 65000 | N |  |  |  |  | Withdrawn |  | Accepted competing offer
C-010 | Kevin | Lee | Database | 2026-04-04 | Network Engineer | IT | Secret | S. Patel | 2026-04-07 | Pass | 2026-04-10 | T. Washington | 4.1 | Pass | 2026-04-14 | 90000 | Y | 2026-04-15 | Initiated | Scheduled |  | Accepted
C-011 | Amanda | Taylor | Job Board | 2026-04-05 | Case Analyst | Analyst | Public Trust | J. Rivera | 2026-04-08 | Pass | 2026-04-11 | L. Chen | 4.4 | Pass | [7 empty] | Interviewed |  |  | Strong candidate
C-012 | Carlos | Rodriguez | Referral | 2026-04-06 | Sr. Case Analyst | Analyst | Secret | S. Patel | 2026-04-09 | Pass | 2026-04-14 | M. Kim | 3.7 | Maybe | [7 empty] | Interviewed |  |  | Needs second interview
C-013 | Lisa | Anderson | Staffing Agency | 2026-04-07 | Training Specialist | Training | Public Trust | J. Rivera | 2026-04-10 | Pass | [11 empty] | Screened
C-014 | Thomas | Martinez | Job Board | 2026-04-08 | Help Desk Tech | IT | Public Trust | S. Patel | 2026-04-11 | Pass | [11 empty] | Screened
C-015 | Rachel | Wilson | Database | 2026-04-09 | Case Analyst | Analyst | Public Trust | J. Rivera | 2026-04-12 | Fail | [11 empty] | Withdrawn |  | Failed phone screen
C-016 | Brian | Harris | Internal | 2026-04-10 | Supervisor | Management | Secret | S. Patel | 2026-04-13 | Pass | 2026-04-17 | T. Washington | 4.6 | [8 empty] | Interviewed
C-017 | Nicole | Clark | Job Board | 2026-04-11 | Data Entry Clerk | Admin | Public Trust | J. Rivera | 2026-04-14 | Pass | [11 empty] | Screened
C-018 | Anthony | Lewis | Staffing Agency | 2026-04-13 | Case Analyst | Analyst | Public Trust | S. Patel | 2026-04-16 | Pass | [11 empty] | Screened
C-019 | Michelle | Walker | Referral | 2026-04-15 | Program Analyst | Analyst | Secret | J. Rivera | [13 empty] | Sourced
C-020 | Daniel | Hall | Database | 2026-04-17 | Case Analyst | Analyst | Public Trust | S. Patel | [13 empty] | Sourced
Formulas:
Days in Current Stage = IF([Start Date]<>"",TODAY()-[Start Date],IF([Offer Accept Date]<>"",TODAY()-[Offer Accept Date],IF([Offer Extended Date]<>"",TODAY()-[Offer Extended Date],IF([Interview Date]<>"",TODAY()-[Interview Date],IF([Phone Screen Date]<>"",TODAY()-[Phone Screen Date],IF([Date Sourced]<>"",TODAY()-[Date Sourced],""))))))

## Interview Scorecard
INTERVIEW SCORECARD
Interview ID | Date | Candidate ID | Candidate Name | Position | Interviewer | Communication | Technical Knowledge | Problem Solving | Experience Relevance | Cultural Fit | Remote Work Readiness | Weighted Total | Recommendation | Strengths | Concerns | Notes
INT-001 | 2026-03-30 | C-001 | Maria Santos | Case Analyst | T. Washington | 4 | 4 | 4 | 5 | 4 | 5 |  | Strong Hire | Excellent remote experience, strong communicator | None noted
INT-002 | 2026-03-31 | C-002 | James Mitchell | Program Support | L. Chen | 4 | 3 | 3 | 4 | 4 | 4 |  | Hire | Good organizational skills | Limited govt experience
INT-003 | 2026-04-01 | C-003 | Aisha Johnson | IT Support Spec | M. Kim | 5 | 5 | 4 | 5 | 4 | 4 |  | Strong Hire | Deep technical knowledge, certs current | Relocating soon
INT-004 | 2026-04-02 | C-004 | Robert Williams | Sr. Analyst | T. Washington | 4 | 4 | 4 | 4 | 4 | 3 |  | Hire | Solid analytical background | Remote readiness needs setup
INT-005 | 2026-04-03 | C-005 | Priya Sharma | Data Entry Clerk | L. Chen | 3 | 3 | 3 | 4 | 4 | 4 |  | Hire | Accurate and detail-oriented | Speed below benchmark
INT-006 | 2026-04-04 | C-006 | David Thompson | QA Specialist | M. Kim | 4 | 4 | 5 | 4 | 5 | 4 |  | Strong Hire | QA methodology expert | None noted
INT-007 | 2026-04-07 | C-007 | Sarah Brown | Case Analyst | T. Washington | 4 | 3 | 4 | 4 | 4 | 4 |  | Hire | Eager learner, positive attitude | Needs training on systems
INT-008 | 2026-04-08 | C-008 | Michael Davis | Security Analyst | L. Chen | 5 | 5 | 5 | 5 | 4 | 4 |  | Strong Hire | Exceptional security knowledge | TS clearance timeline
INT-009 | 2026-04-09 | C-009 | Jennifer Garcia | Program Support | M. Kim | 3 | 3 | 3 | 3 | 4 | 4 |  | Maybe | Pleasant demeanor | Lacks relevant experience | Withdrew after interview
INT-010 | 2026-04-10 | C-010 | Kevin Lee | Network Engineer | T. Washington | 4 | 5 | 4 | 4 | 3 | 4 |  | Hire | Strong networking skills | Limited remote tool experience
INT-011 | 2026-04-11 | C-011 | Amanda Taylor | Case Analyst | L. Chen | 5 | 4 | 4 | 5 | 5 | 4 |  | Strong Hire | Outstanding communication | None noted
INT-012 | 2026-04-14 | C-012 | Carlos Rodriguez | Sr. Case Analyst | M. Kim | 3 | 4 | 3 | 4 | 3 | 4 |  | Maybe | Good technical skills | Communication needs improvement | Second interview recommended
INT-013 | 2026-04-17 | C-016 | Brian Harris | Supervisor | T. Washington | 5 | 4 | 4 | 5 | 5 | 4 |  | Strong Hire | Leadership experience, mentoring skills | Salary expectations high
INT-014 | 2026-04-08 | C-001 | Maria Santos | Case Analyst | L. Chen | 4 | 4 | 5 | 5 | 4 | 5 |  | Strong Hire | Confirmed strong fit | None | Second opinion interview
INT-015 | 2026-04-10 | C-004 | Robert Williams | Sr. Analyst | M. Kim | 4 | 4 | 3 | 4 | 4 | 4 |  | Hire | Analytical depth | Problem solving average

## E-QIP Tracker
E-QIP / SECURITY CLEARANCE TRACKER
Employee ID | Last Name | First Name | Position | Clearance Level Required | eQIP Account Created | eQIP Acct Date | OF-306 Submitted | OF-306 Date | eQIP Initiated Date | eQIP Submitted Date | Agency Received Date | Fingerprints Scheduled | Fingerprints Completed | Interim Requested | Interim Decision | Interim Date | Investigation Opened | Investigation Type | Adjudication Date | Final Decision | Final Clearance Date | Expiration Date | Continuous Eval | Status | Days in Stage | Notes
E-001 | Santos | Maria | Case Analyst | Public Trust | Y | 2026-03-28 | Y | 2026-03-29 | 2026-03-30 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-03 | N |  |  | 2026-04-05 | T1 | 2026-04-12 | Favorable | 2026-04-12 | 2031-04-12 | Y | Complete | 0
E-002 | Mitchell | James | Program Support | Public Trust | Y | 2026-03-29 | Y | 2026-03-30 | 2026-03-31 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-04 | N |  |  | 2026-04-06 | T1 | 2026-04-14 | Favorable | 2026-04-14 | 2031-04-14 | Y | Complete | 0
E-003 | Johnson | Aisha | IT Support Spec | Secret | Y | 2026-03-30 | Y | 2026-03-31 | 2026-04-01 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-05 | Y | Granted | 2026-04-07 | 2026-04-08 | T3 |  |  |  |  | N | Investigation | 12 | Interim granted
E-004 | Williams | Robert | Sr. Analyst | Secret | Y | 2026-04-01 | Y | 2026-04-02 | 2026-04-03 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-07 | Y | Pending |  |  | T3 |  |  |  |  | N | Interim Pending | 14 | Awaiting interim decision
E-005 | Sharma | Priya | Data Entry Clerk | Public Trust | Y | 2026-04-02 | Y | 2026-04-03 | 2026-04-04 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-08 | N |  |  | 2026-04-09 | T1 | 2026-04-16 | Favorable | 2026-04-16 | 2031-04-16 | Y | Complete | 0
E-006 | Thompson | David | QA Specialist | Public Trust | Y | 2026-04-03 | Y | 2026-04-04 | 2026-04-05 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-09 | N |  |  | 2026-04-10 | T1 | 2026-04-18 | Favorable | 2026-04-18 | 2031-04-18 | Y | Complete | 0
E-007 | Brown | Sarah | Case Analyst | Public Trust | Y | 2026-04-05 | Y | 2026-04-06 | 2026-04-07 | 2026-04-09 | 2026-04-10 |  |  | N |  |  |  | T1 |  |  |  |  | N | Submitted | 10
E-008 | Davis | Michael | Security Analyst | TS | Y | 2026-04-06 | Y | 2026-04-07 | 2026-04-08 | 2026-04-10 |  | 2026-04-12 |  | Y | Pending |  |  | T5 |  |  |  |  | N | eQIP Submitted | 10 | TS timeline ~6-12 months
E-009 | Lee | Kevin | Network Engineer | Secret | Y | 2026-04-08 | Y | 2026-04-09 | 2026-04-10 |  |  |  |  | N |  |  |  | T3 |  |  |  |  | N | eQIP Initiated | 10
E-010 | Taylor | Amanda | Case Analyst | Public Trust | Y | 2026-04-10 | Y | 2026-04-11 | 2026-04-12 |  |  |  |  | N |  |  |  | T1 |  |  |  |  | N | OF-306 Submitted | 9
E-011 | Harris | Brian | Supervisor | Secret | Y | 2026-04-12 | N | [6 empty] | N |  |  |  | T3 |  |  |  |  | N | Account Created | 8 | Awaiting OF-306
E-012 | Rodriguez | Carlos | Sr. Case Analyst | Secret | N |  | N | [6 empty] | N |  |  |  | T3 |  |  |  |  | N | Not Started | 6 | Pending hire decision
E-013 | Clark | Nicole | Data Entry Clerk | Public Trust | N |  | N | [6 empty] | N |  |  |  | T1 |  |  |  |  | N | Not Started | 0 | Pending screening
E-014 | Lewis | Anthony | Case Analyst | Public Trust | N |  | N | [6 empty] | N |  |  |  | T1 |  |  |  |  | N | Not Started | 0 | Pending screening
E-015 | Walker | Michelle | Program Analyst | Secret | N |  | N | [6 empty] | N |  |  |  | T3 |  |  |  |  | N | Not Started | 0 | Not yet sourced

## Employee Roster
EMPLOYEE ROSTER — Master List
Employee ID | Last Name | First Name | Email | Phone | Position Title | Labor Category | Contract | Supervisor | Team | Hire Date | Start Date | Status | Clearance Level | Clearance Status | Equip Shipped | Equip Delivered | Equip Verified | Workspace Attest | VPN Active | Remote Readiness | Training Status | Training Complete Date | Nesting Start | Nesting End | OJT Complete | Current QA Score | QA Trend | 30-Day Check-in | 60-Day Check-in | 90-Day Check-in | Attrition Risk | Separation Date | Separation Reason | Notes
E-001 | Santos | Maria | m.santos@contractor.gov | 504-555-0101 | Case Analyst | Analyst | GS-SURGE-2026 | T. Washington | Team Alpha | 2026-04-03 | 2026-04-09 | Deployed | Public Trust | Active | 2026-04-05 | 2026-04-07 | Y | Y | Y | Ready | Complete | 2026-04-12 | 2026-04-13 | 2026-04-17 | Y | 88 | Improving | Complete | Pending |  | Low |  |  | Top performer
E-002 | Mitchell | James | j.mitchell@contractor.gov | 504-555-0102 | Program Support | Admin | GS-SURGE-2026 | L. Chen | Team Beta | 2026-04-04 | 2026-04-10 | Deployed | Public Trust | Active | 2026-04-06 | 2026-04-08 | Y | Y | Y | Ready | Complete | 2026-04-13 | 2026-04-14 | 2026-04-18 | Y | 82 | Stable | Complete | Pending |  | Low
E-003 | Johnson | Aisha | a.johnson@contractor.gov | 504-555-0103 | IT Support Spec | IT | GS-SURGE-2026 | M. Kim | IT Support | 2026-04-05 | 2026-04-11 | Deployed | Secret | Interim | 2026-04-07 | 2026-04-09 | Y | Y | Y | Ready | Complete | 2026-04-14 | 2026-04-15 | 2026-04-19 | Y | 91 | Improving | Complete | Pending |  | Low
E-004 | Williams | Robert | r.williams@contractor.gov | 504-555-0104 | Sr. Analyst | Analyst | GS-SURGE-2026 | T. Washington | Team Alpha | 2026-04-06 | 2026-04-14 | Training | Secret | Pending | 2026-04-10 | 2026-04-12 | Y | Y | Y | Ready | In Progress |  |  |  | N |  |  | Pending |  |  | Medium |  |  | Clearance delay
E-005 | Sharma | Priya | p.sharma@contractor.gov | 504-555-0105 | Data Entry Clerk | Admin | GS-SURGE-2026 | L. Chen | Team Beta | 2026-04-07 | 2026-04-13 | Deployed | Public Trust | Active | 2026-04-09 | 2026-04-11 | Y | Y | Y | Ready | Complete | 2026-04-16 | 2026-04-17 | 2026-04-20 | Y | 79 | Declining | Complete |  |  | Medium |  |  | QA trending down
E-006 | Thompson | David | d.thompson@contractor.gov | 504-555-0106 | QA Specialist | Quality | GS-SURGE-2026 | M. Kim | Quality | 2026-04-08 | 2026-04-14 | Deployed | Public Trust | Active | 2026-04-10 | 2026-04-12 | Y | Y | Y | Ready | Complete | 2026-04-17 | 2026-04-18 | 2026-04-20 | Y | 94 | Stable | Complete |  |  | Low
E-007 | Brown | Sarah | s.brown@contractor.gov | 504-555-0107 | Case Analyst | Analyst | GS-SURGE-2026 | T. Washington | Team Alpha | 2026-04-11 | 2026-04-20 | Training | Public Trust | Pending | 2026-04-15 | 2026-04-17 | Y | Y | Y | Ready | In Progress |  |  |  | N |  |  | Pending |  |  | Low
E-008 | Davis | Michael | m.davis@contractor.gov | 504-555-0108 | Security Analyst | Security | GS-SURGE-2026 | M. Kim | Security | 2026-04-12 |  | Onboarding | TS | Pending | 2026-04-16 | 2026-04-18 | Y | Y | N | Pending | Not Started |  |  |  | N | [5 empty] | Medium |  |  | Awaiting TS clearance
E-009 | Lee | Kevin | k.lee@contractor.gov | 504-555-0109 | Network Engineer | IT | GS-SURGE-2026 | M. Kim | IT Support | 2026-04-15 |  | Onboarding | Secret | Pending | 2026-04-17 |  | N | N | N | Blocked | Not Started |  |  |  | N | [5 empty] | Medium |  |  | Equipment in transit
E-010 | Taylor | Amanda | a.taylor@contractor.gov | 504-555-0110 | Case Analyst | Analyst | GS-SURGE-2026 | T. Washington | Team Alpha | 2026-04-18 |  | Onboarding | Public Trust | Pending |  |  | N | N | N | Blocked | Not Started |  |  |  | N | [5 empty] | Low |  |  | Pending offer accept
E-011 | Parker | Jason | j.parker@contractor.gov | 504-555-0111 | Case Analyst | Analyst | GS-SURGE-2026 | L. Chen | Team Beta | 2026-04-03 | 2026-04-09 | Deployed | Public Trust | Active | 2026-04-05 | 2026-04-07 | Y | Y | Y | Ready | Complete | 2026-04-12 | 2026-04-13 | 2026-04-17 | Y | 85 | Stable | Complete | Pending |  | Low
E-012 | Rivera | Carmen | c.rivera@contractor.gov | 504-555-0112 | Case Analyst | Analyst | GS-SURGE-2026 | L. Chen | Team Beta | 2026-04-04 | 2026-04-10 | Deployed | Public Trust | Active | 2026-04-06 | 2026-04-08 | Y | Y | Y | Ready | Complete | 2026-04-13 | 2026-04-14 | 2026-04-18 | Y | 76 | Declining | Complete | Pending |  | High |  |  | Performance concerns
E-013 | Nguyen | Tran | t.nguyen@contractor.gov | 504-555-0113 | Program Support | Admin | GS-SURGE-2026 | T. Washington | Team Alpha | 2026-04-05 | 2026-04-11 | Deployed | Public Trust | Active | 2026-04-07 | 2026-04-09 | Y | Y | Y | Ready | Complete | 2026-04-14 | 2026-04-15 | 2026-04-19 | Y | 87 | Improving | Complete | Pending |  | Low
E-014 | Foster | Derek | d.foster@contractor.gov | 504-555-0114 | Case Analyst | Analyst | GS-SURGE-2026 | L. Chen | Team Beta | 2026-04-06 | 2026-04-13 | Nesting | Public Trust | Active | 2026-04-09 | 2026-04-11 | Y | Y | Y | Ready | Complete | 2026-04-16 | 2026-04-17 |  | N | 81 | Stable | Pending |  |  | Low
E-015 | Kim | Susan | s.kim@contractor.gov | 504-555-0115 | Training Specialist | Training | GS-SURGE-2026 | M. Kim | Training | 2026-04-07 | 2026-04-13 | Deployed | Public Trust | Active | 2026-04-09 | 2026-04-11 | Y | Y | Y | Ready | Complete | 2026-04-14 |  |  | Y | 90 | Stable | Complete |  |  | Low
E-016 | Washington | Tyler | t.washington@contractor.gov | 504-555-0116 | Supervisor | Management | GS-SURGE-2026 | Program Mgr | Management | 2026-03-15 | 2026-03-20 | Deployed | Secret | Active | 2026-03-17 | 2026-03-18 | Y | Y | Y | Ready | Complete | 2026-03-22 |  |  | Y | 95 | Stable | Complete | Complete | Pending | Low
E-017 | Chen | Lisa | l.chen@contractor.gov | 504-555-0117 | Supervisor | Management | GS-SURGE-2026 | Program Mgr | Management | 2026-03-15 | 2026-03-20 | Deployed | Secret | Active | 2026-03-17 | 2026-03-18 | Y | Y | Y | Ready | Complete | 2026-03-22 |  |  | Y | 93 | Stable | Complete | Complete | Pending | Low
E-018 | Patel | Sanjay | s.patel@contractor.gov | 504-555-0118 | Recruiting Lead | Recruiting | GS-SURGE-2026 | Program Mgr | Recruiting | 2026-03-10 | 2026-03-15 | Deployed | Public Trust | Active | 2026-03-12 | 2026-03-13 | Y | Y | Y | Ready | Complete | 2026-03-16 |  |  | Y |  |  | Complete | Complete | Complete | Low
E-019 | Martinez | Alex | a.martinez@contractor.gov | 504-555-0119 | Case Analyst | Analyst | GS-SURGE-2026 | T. Washington | Team Alpha | 2026-04-03 | 2026-04-09 | Separated | Public Trust | Active | 2026-04-05 | 2026-04-07 | Y | Y | Y | Ready | Complete | 2026-04-12 | 2026-04-13 | 2026-04-17 | Y | 72 | Declining | Complete |  |  |  | 2026-04-18 | Voluntary - personal reasons | Returned equipment
E-020 | Brooks | Dana | d.brooks@contractor.gov | 504-555-0120 | Help Desk Tech | IT | GS-SURGE-2026 | M. Kim | IT Support | 2026-04-10 | 2026-04-16 | Training | Public Trust | Active | 2026-04-12 | 2026-04-14 | Y | Y | Y | Ready | In Progress |  |  |  | N |  |  | Pending |  |  | Low

## Staffing Dashboard
STAFFING DASHBOARD — Workforce Operations View
HEADCOUNT BY STATUS |  |  | HEADCOUNT BY TEAM |  | HEADCOUNT BY SUPERVISOR |  | RAMP PLAN vs ACTUAL
Deployed |  |  | Team Alpha |  | T. Washington |  | Period | Actual | Target
Training |  |  | Team Beta |  | L. Chen |  | Pre-Surge | 3 | 3
Nesting |  |  | IT Support |  | M. Kim |  | Week 1 | 10 | 12
Onboarding |  |  | Quality |  | Program Mgr |  | Week 2 | 18 | 20
Separated |  |  | Security |  |  |  | Week 3 | 25 | 28
TOTAL ACTIVE |  |  | Training |  |  |  | Week 4 (Plan) | 32 | 35
Management
Recruiting
EQUIPMENT TRACKING SUMMARY |  |  |  | REMOTE READINESS |  | TRAINING PIPELINE
Metric | Count | Rate |  | Ready |  | Complete
Total Employees |  |  |  | Pending |  | In Progress
Equipment Shipped |  |  |  | Blocked |  | Not Started
Equipment Delivered
Equipment Verified
Workspace Attested
VPN Active

## Retention Tracker
RETENTION TRACKER
Employee ID | Name | Cohort | Hire Date | 30-Day Check-in Date | 30-Day Status | 30-Day Score | 60-Day Check-in Date | 60-Day Status | 60-Day Score | 90-Day Check-in Date | 90-Day Status | 90-Day Score | Engagement Score | Attrition Risk | Separation Date | Separation Reason | Tenure Days | Notes
E-001 | Maria Santos | Cohort 1 | 2026-04-03 | 2026-05-03 | Complete | 4.2 |  | Pending |  |  |  |  | 4 | Low
E-002 | James Mitchell | Cohort 1 | 2026-04-04 | 2026-05-04 | Complete | 3.8 |  | Pending |  |  |  |  | 3.5 | Low
E-003 | Aisha Johnson | Cohort 1 | 2026-04-05 | 2026-05-05 | Complete | 4.5 |  | Pending |  |  |  |  | 4.3 | Low
E-004 | Robert Williams | Cohort 1 | 2026-04-06 | 2026-05-06 | Pending | [7 empty] | 3.2 | Medium |  |  |  | Clearance causing frustration
E-005 | Priya Sharma | Cohort 1 | 2026-04-07 | 2026-05-07 | Pending | [7 empty] | 3 | Medium |  |  |  | QA scores declining
E-006 | David Thompson | Cohort 1 | 2026-04-08 | 2026-05-08 | Pending | [7 empty] | 4.5 | Low
E-007 | Sarah Brown | Cohort 1 | 2026-04-11 | 2026-05-11 | Pending | [7 empty] | 3.8 | Low
E-011 | Jason Parker | Cohort 1 | 2026-04-03 | 2026-05-03 | Complete | 4 |  | Pending |  |  |  |  | 3.9 | Low
E-012 | Carmen Rivera | Cohort 1 | 2026-04-04 | 2026-05-04 | Complete | 2.8 |  | Pending |  |  |  |  | 2.5 | High |  |  |  | Expressed dissatisfaction
E-013 | Tran Nguyen | Cohort 1 | 2026-04-05 | 2026-05-05 | Complete | 4.1 |  | Pending |  |  |  |  | 4 | Low
E-014 | Derek Foster | Cohort 1 | 2026-04-06 | 2026-05-06 | Pending | [7 empty] | 3.6 | Low
E-015 | Susan Kim | Cohort 1 | 2026-04-07 | 2026-05-07 | Pending | [7 empty] | 4.2 | Low
E-016 | Tyler Washington | Pre-Surge | 2026-03-15 | 2026-04-14 | Complete | 4.8 | 2026-05-14 | Complete | 4.7 |  | Pending |  | 4.9 | Low
E-017 | Lisa Chen | Pre-Surge | 2026-03-15 | 2026-04-14 | Complete | 4.6 | 2026-05-14 | Complete | 4.5 |  | Pending |  | 4.7 | Low
E-018 | Sanjay Patel | Pre-Surge | 2026-03-10 | 2026-04-09 | Complete | 4.3 | 2026-05-09 | Complete | 4.4 | 2026-06-08 | Pending |  | 4.5 | Low
E-019 | Alex Martinez | Cohort 1 | 2026-04-03 | 2026-05-03 | Complete | 2.5 | [6 empty] | 2 | High | 2026-04-18 | Voluntary - personal reasons |  | Left during nesting phase
E-020 | Dana Brooks | Cohort 2 | 2026-04-10 | 2026-05-10 | Pending | [7 empty] | 3.7 | Low
E-008 | Michael Davis | Cohort 2 | 2026-04-12 | 2026-05-12 | Pending | [7 empty] | 3.4 | Medium |  |  |  | Clearance uncertainty
E-009 | Kevin Lee | Cohort 2 | 2026-04-15 | 2026-05-15 | Pending | [7 empty] | 3.3 | Medium |  |  |  | Equipment delays
E-010 | Amanda Taylor | Cohort 2 | 2026-04-18 | 2026-05-18 | Pending | [7 empty] | 3.5 | Low

## Risk Register
RISK REGISTER
Risk ID | Category | Description | Likelihood | Impact | Risk Score | Risk Level | Owner | Mitigation Strategy | Contingency Plan | Status | Date Identified | Target Resolution | Days Open | Trend | Notes
R-001 | Security | Clearance processing delays exceeding 90 days for Secret-level positions | 4 | 5 |  |  | FSO/Security | Pre-submit eQIP packages; engage agency POC for status updates | Request interim clearances for critical roles; reassign to non-cleared tasks | Open | 2026-03-25 | 2026-06-30 |  | Increasing | Top risk
R-002 | Remote-Specific | Remote workspace fails security requirements for CUI handling | 3 | 5 |  |  | FSO/Security | Mandate workspace attestation before equipment shipment; conduct video verification | Provide co-working space stipend at approved SCIFs | Open | 2026-03-25 | 2026-05-15 |  | Stable
R-003 | Technical | VPN capacity insufficient for simultaneous remote connections | 3 | 4 |  |  | IT Lead | Load test VPN before surge; procure additional licenses | Deploy backup VPN gateway; stagger shift schedules | Open | 2026-03-26 | 2026-05-01 |  | Decreasing | Capacity expanded
R-004 | Operational | Equipment shipping delays due to supply chain disruptions | 4 | 4 |  |  | IT Lead | Order 20% buffer stock; use multiple vendors; expedited shipping | Loan personal devices with MDM enrollment temporarily | Open | 2026-03-26 | 2026-05-15 |  | Increasing
R-005 | Compliance | Multi-state tax withholding and labor law compliance gaps | 3 | 4 |  |  | HR Manager | Engage multi-state payroll provider; map employee locations to state requirements | Contract with employment law firm for state-specific guidance | Open | 2026-03-27 | 2026-05-30 |  | Stable
R-006 | Personnel | Attrition spike during first 30 days exceeding 15% threshold | 4 | 4 |  |  | HR Manager | Implement structured onboarding; assign buddy mentors; conduct weekly check-ins | Activate staffing agency rapid-fill agreements; maintain warm candidate bench | Open | 2026-03-27 | 2026-05-15 |  | Increasing | 1 separation so far
R-007 | Operational | Training bottleneck — insufficient trainer-to-trainee ratio | 3 | 3 |  |  | Training Lead | Hire additional trainers; develop self-paced e-learning modules | Deploy recorded training sessions; extend training timeline by 1 week | Mitigating | 2026-03-28 | 2026-05-01 |  | Stable | Added e-learning
R-008 | Security | Insider threat risk elevated with rapid onboarding of unknown personnel | 3 | 5 |  |  | FSO/Security | Implement enhanced monitoring; enforce least-privilege access; UAM tools | Immediate access revocation protocol; incident response plan activation | Open | 2026-03-28 | 2026-06-30 |  | Stable
R-009 | Compliance | Data spill — CUI transmitted via unapproved channels by new hires | 3 | 5 |  |  | FSO/Security | Mandatory CUI handling training before system access; DLP tools on endpoints | Data spill response procedure; notify agency within 1 hour; contain and remediate | Open | 2026-03-29 | 2026-06-30 |  | Stable
R-010 | Security | CUI handling violations in remote environments | 3 | 5 |  |  | FSO/Security | Enforce endpoint encryption; disable USB ports; monitor print queues | Remote workspace spot-check audits; retrain and re-certify | Open | 2026-03-29 | 2026-06-30 |  | Stable
R-011 | Security | Interim clearance denials blocking critical role deployment | 3 | 4 |  |  | FSO/Security | Pre-screen candidates for disqualifying factors; submit complete packages | Reassign to non-sensitive roles; backfill with cleared personnel | Open | 2026-03-30 | 2026-05-30 |  | Stable
R-012 | Security | Polygraph backlog delaying TS-SCI positions | 4 | 3 |  |  | FSO/Security | Schedule polygraphs immediately upon offer acceptance; coordinate with agency | Deploy to non-poly positions; request agency prioritization | Open | 2026-03-30 | 2026-07-31 |  | Increasing
R-013 | Compliance | Foreign contact or foreign travel disclosures creating investigation delays | 2 | 4 |  |  | FSO/Security | Pre-screen for foreign contacts during interview; prepare supplemental docs | Assign to domestic-only, non-sensitive roles pending resolution | Accepted | 2026-03-31 | 2026-06-30 |  | Stable
R-014 | Operational | Drug testing logistics — remote employees in areas without testing centers | 3 | 3 |  |  | HR Manager | Map testing locations near each employee; mobile testing services | Delay start dates until testing confirmed; virtual observed testing | Mitigating | 2026-03-31 | 2026-05-15 |  | Decreasing | Mobile testing arranged
R-015 | Technical | Badge/PIV provisioning delays for system access | 3 | 4 |  |  | IT Lead | Pre-order blank PIV cards; coordinate with HSPD-12 enrollment stations | Issue temporary credentials with limited access; extend enrollment hours | Open | 2026-04-01 | 2026-05-30 |  | Stable
R-016 | Compliance | Social media screening revealing derogatory information post-hire | 2 | 3 |  |  | FSO/Security | Conduct social media screening during pre-employment; document findings | Suitability review board determination; separation if warranted | Accepted | 2026-04-01 | 2026-06-30 |  | Stable
R-017 | Security | Reciprocity delays — prior clearances not transferring between agencies | 3 | 4 |  |  | FSO/Security | Verify DISS/Scattered Castles records early; submit reciprocity requests immediately | Request interim clearance; engage agency security office directly | Open | 2026-04-02 | 2026-06-30 |  | Stable
R-018 | Operational | Lost or stolen equipment in transit or at remote locations | 2 | 4 |  |  | IT Lead | Full disk encryption; asset tracking with GPS; signature-required delivery | Remote wipe capability; file police report; replace within 48 hours | Open | 2026-04-02 | 2026-06-30 |  | Stable
R-019 | Remote-Specific | Unauthorized telework locations — employees working from unapproved sites | 3 | 4 |  |  | HR Manager | Require telework location approval; GPS check-in; random workspace audits | Immediate VPN access suspension; formal counseling; potential separation | Open | 2026-04-03 | 2026-05-30 |  | Stable
R-020 | Personnel | Quality degradation as new hires ramp up without adequate coaching | 4 | 4 |  |  | QA Lead | Implement 100% monitoring during nesting; daily coaching sessions; buddy system | Extend nesting period; remove from production; intensive remediation training | Open | 2026-04-03 | 2026-05-15 |  | Increasing | Monitoring active
Formulas:
Days Open = IF([Status]="Closed",0,TODAY()-[Date Identified])

## RACI Matrix
RACI MATRIX — Surge Operations
Task # | Task Description | Program Manager | Recruiting Lead | HR Manager | FSO/Security | IT Lead | Training Lead | QA Lead | Supervisors | Contracts | Finance
1 | Finalize surge headcount requirements | R | C | C | I | I | I | I | I | A | C
2 | Submit staffing plan to COR | R | I | I | I | I | I | I | I | A | I
3 | Define remote work policies | A | I | R | C | C | I | I | C | I | I
4 | Post surge positions on job boards | A | R | C | I | I | I | I | I | I | I
5 | Activate staffing agency contracts | A | R | I | I | I | I | I | I | C | R
6 | Submit SAAR forms for system access | I | I | I | R | C | I | I | I | A | I
7 | Order laptops and peripherals | A | I | I | I | R | I | I | I | C | C
8 | Provision VPN accounts and MFA tokens | I | I | I | C | R | I | I | I | I | I
9 | Develop virtual training curriculum | A | I | I | C | C | R | C | C | I | I
10 | Prepare onboarding packets | I | C | R | C | C | C | I | C | I | I
11 | Screen and interview candidates | A | R | C | I | I | I | I | C | I | I
12 | Initiate eQIP accounts | I | I | I | R | I | I | I | I | A | I
13 | Ship equipment to remote locations | I | I | I | I | R | I | I | I | I | C
14 | Conduct Day 1 orientation | A | C | R | C | C | C | I | C | I | I
15 | Launch security awareness training | I | I | I | A | I | R | I | I | I | I
16 | Complete candidate interviews | I | R | I | I | I | I | I | A | I | I
17 | Collect OF-306 forms | I | I | C | R | I | I | I | I | I | I
18 | Verify remote workspace attestation | I | I | I | A | R | I | I | C | I | I
19 | Begin role-specific training | A | I | I | I | I | R | I | C | I | I
20 | Establish QA monitoring schedule | A | I | I | I | I | C | R | C | I | I
21 | Extend offers to candidates | A | R | C | I | I | I | I | I | C | C
22 | Schedule fingerprint appointments | bar: I A A A to I I I C
23 | Confirm VPN connectivity | I | I | I | I | R | I | I | C | I | I
24 | Administer training knowledge checks | I | I | I | I | I | R | C | C | I | I
25 | Complete I-9 verification | I | I | R | I | I | I | I | I | A | I
26 | Conduct live QA monitoring | I | I | I | I | I | I | R | C | I | I
27 | Review ramp progress vs plan | R | C | C | C | C | C | C | C | A | C
28 | Source Cohort 2 candidates | A | R | I | I | I | I | I | I | I | I
29 | Submit interim clearance requests | I | I | I | R | I | I | I | I | A | I
30 | Order Cohort 2 equipment | A | I | I | I | R | I | I | I | C | C
31 | Transition Cohort 1 to nesting | A | I | I | I | I | R | C | R | I | I
32 | Conduct 7-day check-in surveys | I | I | R | I | I | I | I | C | I | I
33 | Calibrate QA scoring | A | I | I | I | I | C | R | C | I | I
34 | Update attrition risk assessment | R | C | C | I | I | I | C | C | I | I
35 | Prepare surge progress briefing for COR | R | C | C | C | C | C | C | I | A | C
36 | Conduct CUI handling spot checks | I | I | I | R | C | I | I | C | I | I
37 | Audit endpoint protection compliance | I | I | I | C | R | I | I | I | I | I
38 | Process multi-state tax registrations | I | I | R | I | I | I | I | I | C | A

## QA Monitoring
QA MONITORING LOG
Monitoring ID | Date | Employee ID | Employee Name | Supervisor | Monitoring Type | Communication | Process Adherence | Accuracy | Compliance | Customer Service | System Navigation | Documentation | Weighted Score | Pass/Fail | Critical Error | Strengths | Areas for Improvement | Coaching Provided | Team Average
QA-001 | 2026-04-14 | E-001 | Maria Santos | T. Washington | Live | 5 | 4 | 5 | 4 | 5 | 4 | 4 |  |  | N | Excellent communication, empathetic tone | Minor documentation gaps | Y
QA-002 | 2026-04-14 | E-002 | James Mitchell | L. Chen | Live | 4 | 4 | 4 | 4 | 4 | 3 | 4 |  |  | N | Thorough and methodical | System navigation speed | Y | Pass Rate
QA-003 | 2026-04-14 | E-005 | Priya Sharma | L. Chen | Recorded | 3 | 4 | 4 | 4 | 3 | 4 | 3 |  |  | N | Accurate data entry | Customer interaction needs coaching | Y
QA-004 | 2026-04-15 | E-011 | Jason Parker | L. Chen | Live | 4 | 4 | 4 | 5 | 4 | 4 | 4 |  |  | N | Good compliance awareness | Documentation could be more detailed | N | D. Thompson
QA-005 | 2026-04-15 | E-012 | Carmen Rivera | L. Chen | Recorded | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | N | Positive attitude | Multiple areas need improvement | Y | D. Thompson
QA-006 | 2026-04-15 | E-013 | Tran Nguyen | T. Washington | Live | 4 | 5 | 4 | 5 | 4 | 4 | 4 |  |  | N | Exceptional process adherence | None noted | N | D. Thompson
QA-007 | 2026-04-16 | E-001 | Maria Santos | T. Washington | Screen Share | 5 | 5 | 5 | 4 | 5 | 5 | 4 |  |  | N | Outstanding across all categories | Minor compliance protocol gap | N | D. Thompson
QA-008 | 2026-04-16 | E-003 | Aisha Johnson | M. Kim | Live | 5 | 5 | 4 | 5 | 4 | 5 | 5 |  |  | N | Deep technical knowledge, excellent documentation | None | N | D. Thompson
QA-009 | 2026-04-16 | E-005 | Priya Sharma | L. Chen | Live | 3 | 3 | 4 | 4 | 3 | 3 | 3 |  |  | N | Improved accuracy from last session | Communication still below standard | Y | D. Thompson
QA-010 | 2026-04-17 | E-014 | Derek Foster | L. Chen | Live | 4 | 4 | 4 | 4 | 4 | 3 | 4 |  |  | N | Solid foundational skills | System navigation — new to platform | Y | D. Thompson
QA-011 | 2026-04-17 | E-002 | James Mitchell | L. Chen | Recorded | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | N | Consistent performance | None significant | N | D. Thompson
QA-012 | 2026-04-17 | E-012 | Carmen Rivera | L. Chen | Screen Share | 3 | 3 | 2 | 3 | 3 | 3 | 3 |  |  | Y | Willingness to learn | Critical accuracy error — wrong case disposition | Y | D. Thompson
QA-013 | 2026-04-18 | E-011 | Jason Parker | L. Chen | Live | 4 | 5 | 4 | 5 | 4 | 4 | 5 |  |  | N | Strong improvement in documentation | None | N | D. Thompson
QA-014 | 2026-04-18 | E-019 | Alex Martinez | T. Washington | Live | 3 | 3 | 3 | 3 | 3 | 2 | 3 |  |  | Y | None notable | Multiple deficiencies — critical navigation errors | Y | D. Thompson
QA-015 | 2026-04-18 | E-013 | Tran Nguyen | T. Washington | Recorded | 5 | 5 | 5 | 5 | 4 | 4 | 4 |  |  | N | Consistent high performer | None | N | D. Thompson
QA-016 | 2026-04-19 | E-001 | Maria Santos | T. Washington | Live | 5 | 5 | 5 | 5 | 5 | 5 | 4 |  |  | N | Role model performance | None | N | D. Thompson
QA-017 | 2026-04-19 | E-006 | David Thompson | M. Kim | Live | 5 | 5 | 5 | 5 | 5 | 4 | 5 |  |  | N | QA expertise evident in own work | None | N | QA Lead
QA-018 | 2026-04-19 | E-005 | Priya Sharma | L. Chen | Screen Share | 4 | 3 | 4 | 4 | 3 | 3 | 3 |  |  | N | Accuracy improving | Communication and navigation still lag | Y | D. Thompson
QA-019 | 2026-04-19 | E-012 | Carmen Rivera | L. Chen | Live | 3 | 3 | 3 | 3 | 3 | 3 | 2 |  |  | N | Slight improvement post-coaching | Documentation deficient — needs template | Y | D. Thompson
QA-020 | 2026-04-20 | E-002 | James Mitchell | L. Chen | Live | 4 | 4 | 5 | 4 | 4 | 4 | 4 |  |  | N | Improved accuracy significantly | None | N | D. Thompson
QA-021 | 2026-04-20 | E-011 | Jason Parker | L. Chen | Recorded | 5 | 5 | 4 | 5 | 4 | 4 | 5 |  |  | N | Top performer in cohort | None | N | D. Thompson
QA-022 | 2026-04-20 | E-014 | Derek Foster | L. Chen | Screen Share | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | N | Consistent solid performance | None significant | N | D. Thompson
QA-023 | 2026-04-20 | E-015 | Susan Kim | M. Kim | Live | 5 | 4 | 5 | 5 | 4 | 5 | 4 |  |  | N | Excellent training methodology | None | N | D. Thompson
QA-024 | 2026-04-20 | E-003 | Aisha Johnson | M. Kim | Recorded | 5 | 5 | 5 | 5 | 4 | 5 | 5 |  |  | N | Consistent excellence | None | N | D. Thompson
QA-025 | 2026-04-20 | E-013 | Tran Nguyen | T. Washington | Live | 5 | 5 | 5 | 5 | 5 | 4 | 5 |  |  | N | Exceptional — ready for advanced tasks | None | N | D. Thompson

## Compliance Checklist
COMPLIANCE CHECKLIST — Security & Operations
Item # | Category | Requirement | Responsible Party | Due Date | Completion Date | Status | Evidence | Notes
CC-001 | NIST 800-171 | Implement access control policies per NIST 800-171 AC family | FSO/Security | 2026-04-15 | 2026-04-14 | Complete | Policy document v2.1
CC-002 | CUI Handling | Establish CUI marking and handling procedures for remote workforce | FSO/Security | 2026-04-10 | 2026-04-09 | Complete | CUI SOP approved
CC-003 | Workspace | Collect remote workspace attestation forms from all employees | IT Lead | 2026-04-20 | 2026-04-18 | Complete | Attestation forms on file | 2 pending
CC-004 | VPN | Configure split-tunnel VPN prohibition — all traffic through agency VPN | IT Lead | 2026-04-08 | 2026-04-08 | Complete | VPN config audit report
CC-005 | Endpoint Protection | Deploy EDR/endpoint protection on all government-furnished equipment | IT Lead | 2026-04-12 | 2026-04-11 | Complete | EDR deployment report | CrowdStrike deployed
CC-006 | Security Training | Complete annual security awareness training for all personnel | Training Lead | 2026-04-15 | 2026-04-14 | Complete | LMS completion records | 100% Cohort 1
CC-007 | SF-312 | Execute SF-312 Non-Disclosure Agreements for all cleared personnel | FSO/Security | 2026-04-12 | 2026-04-12 | Complete | Signed SF-312s on file
CC-008 | Incident Reporting | Establish security incident reporting procedures and POC list | FSO/Security | 2026-04-08 | 2026-04-07 | Complete | Incident response plan v1.0
CC-009 | MFA | Enforce multi-factor authentication on all system access | IT Lead | 2026-04-10 | 2026-04-10 | Complete | MFA audit log | PIV + PIN enforced
CC-010 | CAC/PIV | Issue CAC/PIV cards to all personnel requiring system access | FSO/Security | 2026-04-20 |  | In Progress |  | 3 pending enrollment
CC-011 | SAAR Forms | Submit System Authorization Access Request forms for all users | FSO/Security | 2026-04-15 | 2026-04-14 | Complete | SAAR tracking log
CC-012 | Removable Media | Implement removable media prohibition policy on all endpoints | IT Lead | 2026-04-12 | 2026-04-11 | Complete | GPO configuration report | USB ports disabled
CC-013 | Wireless Security | Ensure WPA3 or equivalent wireless security at remote locations | IT Lead | 2026-04-18 |  | In Progress |  | Verification in progress
CC-014 | NIST 800-171 | Implement audit and accountability controls per AU family | IT Lead | 2026-04-20 |  | In Progress |  | SIEM configuration ongoing
CC-015 | CUI Handling | Conduct CUI handling training for all personnel with CUI access | Training Lead | 2026-04-18 | 2026-04-17 | Complete | Training completion certificates
CC-016 | NIST 800-171 | Implement identification and authentication controls per IA family | IT Lead | 2026-04-15 | 2026-04-14 | Complete | IA control assessment
CC-017 | Endpoint Protection | Configure automatic OS and application patching on all endpoints | IT Lead | 2026-04-14 | 2026-04-13 | Complete | Patch management report | WSUS configured
CC-018 | Security Training | Complete Insider Threat Awareness training for all personnel | Training Lead | 2026-04-20 |  | In Progress |  | Cohort 2 pending
CC-019 | NIST 800-171 | Implement physical protection controls for remote CUI environments | FSO/Security | 2026-04-22 |  | Not Started |  | Spot checks planned
CC-020 | Workspace | Verify approved privacy screens on all remote monitors | IT Lead | 2026-04-22 |  | Not Started |  | Screens shipped
CC-021 | NIST 800-171 | Implement system and communications protection per SC family | IT Lead | 2026-04-25 |  | Not Started |  | TLS 1.3 enforcement
CC-022 | CUI Handling | Establish CUI destruction procedures for remote environments | FSO/Security | 2026-04-25 |  | Not Started |  | Cross-cut shredder policy
CC-023 | Incident Reporting | Conduct tabletop exercise for data spill response | FSO/Security | 2026-04-28 |  | Not Started |  | Scheduled for Week 4
CC-024 | Security Training | Complete Controlled Environment Security Brief for all remote staff | FSO/Security | 2026-04-30 |  | Not Started
CC-025 | NIST 800-171 | Complete Plan of Action and Milestones (POA&M) for open controls | FSO/Security | 2026-05-01 |  | Not Started

## Alerts
ALERTS — Auto-Flagged Action Items
Priority | Category | Alert Description | Employee/Item | Days Overdue | Action Required | Assigned To | Status
Critical | Security | TS clearance processing stalled — no agency response in 10 days | E-008 Michael Davis | 10 | Escalate to agency security POC; request status update | FSO/Security | Open
Critical | Security | Interim clearance decision pending >14 days | E-004 Robert Williams | 14 | Follow up with adjudication office; prepare contingency assignment | FSO/Security | Open
Critical | Operations | Equipment not delivered — employee blocked from starting | E-009 Kevin Lee | 3 | Expedite shipping; provide tracking update to employee | IT Lead | Open
High | Quality | QA score below 80% — critical error flagged | E-012 Carmen Rivera | 0 | Initiate performance improvement plan; assign dedicated coach | QA Lead | Open
High | Quality | QA score declining trend — 3 consecutive sessions below standard | E-005 Priya Sharma | 0 | Schedule coaching session; review training gaps | QA Lead | Open
High | HR | 30-day check-in overdue | E-004 Robert Williams | 6 | Schedule immediate check-in; assess engagement and clearance frustration | HR Manager | Open
High | HR | 30-day check-in overdue | E-005 Priya Sharma | 6 | Schedule immediate check-in; address QA performance concerns | HR Manager | Open
High | Risk | Risk R-001 trending increasing — clearance delays worsening | Risk Register R-001 | 0 | Review mitigation effectiveness; escalate to program manager | FSO/Security | Open
High | Risk | Risk R-006 trending increasing — attrition risk elevated | Risk Register R-006 | 0 | Activate retention measures; review exit interview data | HR Manager | Open
Medium | Recruiting | Candidate C-012 stalled at Interview stage for 6 days — no decision | C-012 Carlos Rodriguez | 6 | Make hire/no-hire decision; schedule second interview if needed | Recruiting Lead | Open
Medium | Operations | Checklist task T-033 in progress past due date | QA Calibration | 1 | Complete calibration exercise; document scoring standards | QA Lead | Open
Medium | Security | eQIP not yet initiated — employee onboarding | E-009 Kevin Lee | 10 | Create eQIP account immediately; begin OF-306 collection | FSO/Security | Open
Medium | Compliance | CAC/PIV cards pending for 3 employees | CC-010 | 0 | Schedule HSPD-12 enrollment appointments | FSO/Security | Open
Medium | Compliance | Wireless security verification incomplete for remote locations | CC-013 | 2 | Send verification checklist to remaining employees | IT Lead | Open
High | Personnel | Recent separation — E-019 attrition risk signal for cohort | E-019 Alex Martinez | 2 | Conduct stay interviews for at-risk employees; review workload | HR Manager | Open

## Change Log
CHANGE LOG — Audit Trail
Change ID | Date | Sheet Affected | Record/Employee | Field Changed | Old Value | New Value | Changed By | Reason
CL-001 | 2026-04-08 | Candidate Pipeline | C-009 Jennifer Garcia | Pipeline Stage | Offered | Withdrawn | S. Patel | Candidate accepted competing offer
CL-002 | 2026-04-09 | Employee Roster | E-001 Maria Santos | Status | Training | Deployed | T. Washington | Completed training and nesting successfully
CL-003 | 2026-04-10 | E-QIP Tracker | E-003 Aisha Johnson | Interim Decision | Pending | Granted | FSO | Agency granted interim Secret clearance
CL-004 | 2026-04-12 | Risk Register | R-003 | Trend | Stable | Decreasing | IT Lead | VPN capacity expanded with additional gateway
CL-005 | 2026-04-14 | QA Monitoring | E-012 Carmen Rivera | Critical Error | N | Y | D. Thompson | Critical accuracy error identified in case disposition
CL-006 | 2026-04-15 | Surge Checklist | T-033 | Status | Not Started | In Progress | QA Lead | QA calibration exercise initiated
CL-007 | 2026-04-16 | Employee Roster | E-014 Derek Foster | Status | Training | Nesting | L. Chen | Transitioned to nesting phase
CL-008 | 2026-04-18 | Employee Roster | E-019 Alex Martinez | Status | Deployed | Separated | HR Manager | Voluntary separation — personal reasons
CL-009 | 2026-04-18 | Retention Tracker | E-019 Alex Martinez | Separation Date |  | 2026-04-18 | HR Manager | Processed separation paperwork
CL-010 | 2026-04-20 | Risk Register | R-006 | Trend | Stable | Increasing | Program Manager | Attrition risk elevated following E-019 separation