## Slide 1
RAPID WORKFORCE ACTIVATION PROTOCOL
SURGE HIRING PLAYBOOK
GOVERNMENT CONTRACT – RAPID WORKFORCE ACTIVATION PROTOCOL
From Trigger to Deployment in 72 Hours
APRIL 2026 | VERSION 1.0 | PREPARED BY KELLY
CONFIDENTIAL

## Slide 2
PURPOSE & SCOPE — REMOTE WORKFORCE
This playbook establishes a repeatable, compliance-ready framework for rapidly scaling a remote contract workforce — covering remote equipment logistics, virtual onboarding, home workspace verification, and remote security compliance across four critical activation contexts.
FEMA DISASTER DECLARATIONS
Activate full remote surge protocol within 24 hours of declaration; deploy equipment kits & VPN credentials
FEDERAL TASK ORDER ACTIVATIONS
Targeted remote hiring sprints for scope increases >25% with virtual onboarding tracks
EMERGENCY STAFFING DIRECTIVES
Expedited remote screening, home workspace verification & same-week virtual onboarding
SEASONAL / PLANNED SURGES
Remote pipeline refresh 60 days prior — security compliance & equipment pre-staging
LABOR CATEGORIES:
Field Staff
Technical Specialists
Administrative Support
Program Management
Aligned with OPM Talent Surge guidance, distributed workforce best practices, and FEMA principles:
Prepare ·
Respond ·
Recover ·
Mitigate

## Slide 3
ACTIVATION TRIGGERS
Five scenarios that initiate the Surge Hiring Protocol — know the trigger, know the action.
TRIGGER 1
FEMA Disaster Declaration
Action: Activate full surge protocol within 24 hours
TRIGGER 2
Task Order Modification (>25% Scope Increase)
Action: Initiate targeted hiring sprint
TRIGGER 3
Staffing Shortfall Alert (Vacancy >15%)
Action: Deploy pre-qualified bench candidates immediately
TRIGGER 4
Client Emergency Request
Action: Expedited screening and same-week onboarding
TRIGGER 5
Seasonal / Planned Surge
Action: Begin pipeline refresh 60 days prior
Any single trigger activates the 4-Phase Rapid Hiring Workflow
SURGE HIRING PLAYBOOK

## Slide 4
RAPID WORKFORCE ACTIVATION — REMOTE OPERATIONS
4-PHASE RAPID HIRING WORKFLOW
From ongoing readiness to full remote deployment — a structured sprint to staff your contract in 72 hours.
PHASE 1
PREPARE
Ongoing / Pre-Event
Maintain pre-vetted bench at min 20% above headcount
Keep clearances current across all labor categories
Pre-stage remote equipment kits (laptops, peripherals, tokens)
Establish shipping logistics & carrier SLAs for rapid delivery
Conduct quarterly pipeline readiness drills
PHASE 2
ACTIVATE
0 – 24 Hours
PM issues Surge Activation Notice
Pull pre-qualified candidates by labor category
Verify remote workspace meets security & ergonomic standards
Provision VPN credentials & secure access profiles
Initiate compliance review (SCA, EEO/OFCCP)
PHASE 3
DEPLOY
24 – 72 Hours
Extend conditional offers to candidates
Conduct virtual onboarding sessions via video platform
Complete I-9 (remote verification) and e-screening
Deliver remote training modules & tool walkthroughs
Upload records to CMS
PHASE 4
SUSTAIN
72 Hours – 30 Days
7-day and 30-day virtual performance check-ins
Remote monitoring of productivity & connectivity metrics
Backfill pipeline within 14 days
Capture lessons learned via virtual retrospectives
Target: From trigger event to fully deployed remote workforce in 72 hours — with virtual sustainment tracking through Day 30.

## Slide 5
WEEK 0
PRE-PLANNING (WEEK 0)
This is where 80% of success is determined.
CONTRACT REALITY & SCOPE LOCK
Exact roles + headcount by labor category
Clearance requirements (active vs sponsorable)
Work location + facility requirements
Start date + ramp schedule
Budget + rate caps
Billable vs non-billable lag
Compliance constraints
SLA expectations
REMOTE READINESS
Equipment inventory & shipping logistics ⬤ CRITICAL PATH
Home workspace attestation requirements
VPN & endpoint security provisioning
State-level employment compliance (multi-state hiring)
Account for 5–7 day shipping buffer in ramp timeline
+5–7 DAYS TO TIMELINE
BUILD THE HIRING MACHINE
Assign hiring pods (1 recruiter per 15–25 hires/mo)
Assign coordinators (1 per 2–3 recruiters)
Dedicated hiring managers
Pre-build JDs / interview guides / scorecards
Pre-approve compensation bands
Offer templates aligned to contract rates
"
Don't start recruiting until you've pressure-tested exact roles, headcount, timelines, clearance requirements, and remote logistics — equipment shipping alone adds 5–7 days.
"

## Slide 6
PIPELINE STRATEGY
REMOTE-FIRST
Remote hiring unlocks a national candidate pool — coverage ratio drops to 2–3× with faster interview cycles.
1
INTERNAL ATS MINING
Mine existing database first — now includes nationwide candidates previously filtered by location.
2
REFERRALS
Incentivize heavily — remote roles widen referral networks across all time zones.
3
CLEARANCE JOB BOARDS
Target cleared talent pools — remote expands reach beyond local secure facilities.
4
STAFFING PARTNERS
Pre-vetted agencies on standby — no travel/facility coordination needed.
5
PASSIVE SOURCING
LinkedIn and niche groups — national pool eliminates geo-filtering constraints.
50 hires needed
=
100–150
(2–3× coverage)
WORKSPACE VERIFIED
EQUIPMENT SHIPPED
NEW STAGE: WORKSPACE VERIFIED
Home office meets security & ergonomic standards
Network connectivity verified before start date
NEW STAGE: EQUIPMENT SHIPPED
Laptop, peripherals & credentials shipped pre-Day 1
Track delivery to confirm onboarding readiness
PRE-CLOSE STRATEGY
— Start closing before offers
Timezone management is a key scheduling factor for distributed interviews
Build a Warm Bench — pre-qualified candidates ready to deploy
Fast Virtual Interviews — no travel or facility coordination needed
Soft-Close on Comp & Timeline — align expectations before offer stage

## Slide 7
REMOTE EXECUTION — FIRST 30 DAYS
Stand up remote operations fast — equip, train, and monitor from anywhere
WEEK 1–2
Remote Setup & Onboarding
Ship equipment to all new hires within 24–48 hours
VPN & security credentials provisioned before Day 1
Home workspace verification via photo/video checklist
Virtual orientation sessions scheduled & recorded
Daily standups: connectivity issues, equipment status, IT provisioning, access confirmations
WEEK 2–3
Virtual Training & Shadowing
Virtual instructor-led training (VILT) sessions daily
Screen-share shadowing with tenured agents
Virtual nesting with real-time coach support
Simulated call practice via screen-share breakout rooms
Knowledge checks & certification gating before go-live
WEEK 3–4
Monitor & Optimize Remotely
Remote monitoring tools active (screen recording, idle alerts)
Daily virtual check-ins with team leads & supervisors
Live performance dashboards tracking KPIs in real time
Escalate at-risk agents for 1-on-1 virtual coaching
"Remote doesn't mean invisible — measure everything, coach constantly."

## Slide 8
CLEARANCE & SECURITY TRACK
This is where most surge teams fail — especially with remote cleared positions.
STEP 1
Verify Clearance Early
DURING RECRUITER SCREEN — NOT LATER
Clearance level (Secret, TS, TS/SCI)
Last investigation date
Active vs. inactive status
Sponsoring agency
Validate on first call — delays compound
STEP 2
Transfer Strategy
REDUCE TRANSFER FRICTION
Prioritize recently active clearances
Use agencies with smoother reciprocity
Assign a dedicated FSO / security team
Track transfer timelines daily — escalate blockers
STEP 3
Build a Cleared Bench
ALWAYS-READY TALENT POOL
Maintain warm cleared candidates at all times
Pre-interview top prospects quarterly
Engage weekly with touchpoints & updates
Tag by clearance level, location, availability
STEP 4 — REMOTE WORK
Remote-Specific Security Requirements
VPN Provisioning Provision, configure & test VPN access before Day 1. Validate split-tunnel policies.
Endpoint Security Deploy EDR, disk encryption & DLP agents on all remote devices before network access.
COMSEC / Workspace Inspection Remote workspace inspections required for cleared roles — verify secure area & COMSEC compliance.
Data Handling Training No printing CUI at home. Mandatory training on remote handling of classified & controlled data.
MFA Setup Enroll hardware token + biometric MFA before granting any remote system access.
Geographic / CONUS Restrictions Enforce CONUS-only work locations. Block OCONUS VPN & verify geolocation compliance.
CRITICAL: Clearance delays are the #1 cause of missed deployment windows.
Verify clearance on the first call — not at offer stage. Every day of delay adds 3–5 days to deployment. Remote cleared positions require additional security provisioning before any system access is granted.
AVERAGE TRANSFER
4–8 Weeks
BENCH TARGET
20% Above Headcount
VERIFY ON
First Call — Day 0

## Slide 9
DAY ONE LAUNCH PACKET
REMOTE OPERATIONS
The exact checklist your remote teams use the morning agents go live — fully virtual, zero on-site required.
IT
Equipment delivery confirmed
VPN connection tested
Remote desktop access verified
MFA activated on all accounts
Remote troubleshooting channel open
RECRUITING / HR
Virtual orientation via video call
All documents e-signed
I-9 remote verification complete
Background checks initiated
Offer letters digitally signed
Benefits enrollment confirmed online
OPERATIONS
Virtual war room channel joined
Communication tools installed
Remote escalation paths active
Daily virtual standup scheduled
Reporting dashboards live
TRAINING
VILT schedule distributed
Virtual mentor assigned
LMS credentials provided
Compliance modules completed
QA expectations set
Every card must show ALL GREEN before a single remote agent takes a live call. No exceptions.

## Slide 10
THE SUCCESS FORMULA — REMOTE
Five non-negotiable principles for distributed teams that deliver from day one.
1 SPEED
Equipment logistics is the new critical path, not facilities · Ship laptops <48 hrs post-acceptance · Pre-provision VPN, credentials & tools before hardware arrives
2 CANDIDATE EXPERIENCE
Virtual onboarding must feel personal, not transactional · Live video welcome from hiring manager · Personalized first-week agenda delivered before start date
3 COMMUNICATION INFRASTRUCTURE
Define channels, escalation paths & response-time SLAs from day one · Slack/Teams for async · Clear on-call and urgent-issue protocols
4 REMOTE SUPERVISION
Smaller spans of control: 8–10 reports max · Track leading indicators — login times, idle time, task completion — not just output
5 RETENTION
Virtual buddy program pairs every new hire with a peer mentor · The 7-day check-in is make-or-break for early attrition
Ship → Connect → Monitor → Retain Remote-ready in 72 hours
REMOTE SPEED WINS — EQUIP, CONNECT, RETAIN.
CONFIDENTIAL – FOR INTERNAL USE ONLY | APRIL 2026